## Slide 1: Audit Committee ERP project Thursday 26th February 2026
  KPMG. Make the Difference.

## Slide 2
Agenda
01 | High level summary | 03
02 | Timeline | 07
03 | Financial Overview | 17

## Slide 3: High level summary
01

## Slide 4
Key Benefits & Partners
Key benefits
Single solution supporting multi-currency, multi-GAAP, and bilingual (FR/EN) operations—built to scale with ABIVAX growth.
Stronger Compliance & Internal Controls (SOX2-ready), improved audit trail, segregation of duties, approvals, and traceability to meet SOX2 expectations and reduce control gaps.
Standardized P2P workflows with clearer roles and automated steps to reduce manual effort, errors, and cycle times across all employees.
Better Spend, Cash & Commitment Visibility, real-time view of spend, commitments, and cash impact, enabling tighter cost control and better treasury planning.
Faster Close & Reliable Reporting (“Single Source of Truth”), more consistent master data and processes to accelerate period-end close, improve data quality, and enable decision-grade reporting.
Oracle, with its solution Ntesuite, is the ERP preferred partner at this stage. The program will implement the standard NetSuite solution (configured to ABIVAX’s FR/U.S. footprint and compliance needs), and the deployment will be delivered directly by NetSuite’s own implementation teams (editor/vendor-led delivery), ensuring product expertise, alignment with best practices, and faster issue resolution throughout the project and hypercare. Commercial and legal negotiations is starting as of this week.
KPMG supported Abivax in precisely identifying the needs the ERP must address, formalizing these requirements, and leading the selection of the best-fit solution and implementation partner aligned with Abivax’s needs and context.
Going forward, KPMG could continue to support Abivax regarding project management, functional assistance, and change management (currently under discussion)
Notes: Thelma

## Slide 5
Integrator
Editor
Infra
References
IT solution coverage
ERP: NetSuite, including Procurement Mid-Market Cloud Service
Options:
  Middleware: NSIP Oracle Netsuite middleware
  E-invoicing: NetSuite + Avalara
  BI solution: NetSuite Analytics Warehouse
Ennov: Life sciences
ITBMed: Biotech
EFESO: Industrial performance consulting
SaaS public cloud application, hosted in distributed Oracle data centers
Year of creation
Activity and expertise
Workforce
Certifications
Revenue/Turnover
1977
Cloud, ERP
162 000
ISO27001 and SOC2
57,4 B €
Year of creation
Workforce
Revenue/Turnover
Net income
Team locations
1977
162 000
57,4 B €
12,44 B €
All over the world
Selected solution scope:
Editor and integrator informations:
Functional Scope

## Slide 6: Timeline
01

## Slide 7
2026 |  |  |  |  |  |  |  |  |  | 2027 |  | 
March | April | May | June | July | August | September | October | November | December | January | February | March
Organization & Getting Started Sessions
Personnalization session (design phase)
ENGAGE
Enable
Convert
Optimize
DRIVE
Configuration
Data Migration
Integrations
Post Go-Live Support
UAT End to End
Go-Live - Cutover
Kick Off
Go - Live
Timeline: From contract signing to Go-Live
Signing

## Slide 8
Main activities per phases
Activities
ENGAGE
    Final process walkthrough
    Pre-UAT training
    Unit test
    Data migration test
    User Acceptance Test
    Data migration
    User End Training
    Cutover
    Hypercare phase
    Plan for future phases
    Resourcing
    Sales/delivery transition
    Kick-off meeting
    Fundamentals Training
    Detailed planning
Enable
Convert
Optimize
DRIVE
    Review personalization requirements
    Build core configuration
    Configuration walkthroughs
Notes: Thelma

## Slide 9: Financial overview
02

## Slide 10
 |  | Netsuite - Oracle
Overall cost over 3 years |  | 1 024 145,80 €
Overall cost over 5 years |  | 1 398 163,00 €
Overall cost over 10 years |  | 2 333 206,00 €
Sub-total “Build” (One-Off) | 463,120.00 €
Sub-total “Run” Saas (annual) | 187 008,60 €
Total (man days) | 392
Integrator’s average daily rate | 1 135,51 €
Overall cost over 3/5/10 years including Build + Run costs
Run cost on an annual basis
Build cost for the full scope implementation
Man days required for the full scope implementation
Financial overview for the ERP project
Number of users considered | 142
Unit price after discount, per user per year | 779,49€
Run costs details

## Slide 11: Zoom on Financial - Detailed costs for Build
 |  | Netsuite - Oracle
Build | Project management | 20 960,00 €
 | Initialization | 50 640,00 €
 | Solution design | 16 440,00 €
 | Solution implementation | 269 240,00 €
 | Data recovery | 28 720,00 €
 | Acceptance | 11 360,00 €
 | Training | 13 920,00 €
 | Production start-up and assistance | 15 760,00 €
 | Maintenance and user support during the warranty phase | - €
 | Reversibility management | 6 640,00 €
 | Best-of-breed implementation (options) | 11 440,00 €
 | Travel expenses | 18 000,00 €
 | Sub-total “Build” (One-Off) | 463 120,00 €
Total (man days) |  | 392
Integrator's average daily rate |  | 1 135,51 €
Detailed implementation cost
Travel expenses: The travel expense cost is an estimate and needs to be reviewed.
General pricing: The pricing is not the final version of the offer, and some topics still need clarification, particularly the e-invoicing implementation scope which seems understimated.
Comments
Notes: Camille

## Slide 12: Zoom on Financial - Detailed costs for Run
 |  | Netsuite - Oracle
Run | SAAS rent (annual) | 145 899,60 €
 | SaaS rent (annual unit basis) | 779,49 €
 | SaaS rent (monthly basis) | 9 159,00 €
 | SaaS rent (annual basis) | 109 908,00 €
 | Best of Breed SaaS rent (annual basis) | 23 935,80 €
 | Hosting subscription (annual) | - €
 | Other costs (additional environment) | 12 055,80 €
 | TMA (annual) | 41 109,00 €
 | Support (annual basis) | 21 257,40 €
 | TMA rent (annual basis) | 19 851,60 €
 | Other support / maintenance services | - €
 | Sub-total “Run” Saas (annual) | 187 008,60 €
 | Sub-total “Run” Saas (5 years) | 935 043,00 €
Detailed Run cost of the ERP and Best Of Breed solutions
Detailed licences cost
 | Netsuite - Oracle
Unit public price per user per year for Core solution for a full user | 1 097,87 €
Discount proposed on public price | 29%
Unit price per user per year for Core solution for a full user | 779,49 €
License mix | NetSuite SuiteSuccess Financials Premium Cloud Service: 1 for 43K each NetSuite General Access Cloud Service User (full user): 42 for 1K3 each NetSuite Employee Self-Serve Cloud Service Users: 85 for 216 each NetSuite Specialized View and Approve Cloud Service Users: 10 for 336 each NetSuite OneWorld Cloud Service: 1 for 21,6K each NetSuite Procurement Mid-Market Cloud Service: 1 for 6K480 each NetSuite Inventory Management Mid-Market Cloud Service: 1 for 6k480 each
Total amount of licenses for Core solution / per year | 141
Total amounts of licenses per year discounts included / with best of breed solution | 133 843,80 €
Total amount / by number of real Abivax users (142 in RFP) | 942,56 €
Notes: Camille

## Slide 13: Overall costs and first thoughts about TCO
 |  | Netsuite - Oracle
Overall cost over 3 years |  | 1 024 145,80 €
Overall cost over 5 years |  | 1 398 163,00 €
Overall cost over 10 years |  | 2 333 206,00 €
Reminder: Overall cost over 3/5/10 years including Build + Run costs (only implementer’s costs)
Cash-out forecast for Abivax |  |  |  |  |  |  |  |  |  |  |  | 
Editor/Implementer |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | TOTAL
Netsuite - Oracle | Build + T&E + Contingency | 532 588,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 532 588,00 €
 | External support | 162 092,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 0,00 € | 162 092,00 €
 | Run (license cost and TMA) | 187 008,60 € | 187 008,60 € | 187 008,60 € | 198 229,12 € | 210 122,86 € | 222 730,23 € | 236 094,05 € | 250 259,69 € | 265 275,27 € | 281 191,79 € | 2 224 928,82 €
 | TOTAL | 881 688,60 € | 187 008,60 € | 187 008,60 € | 198 229,12 € | 210 122,86 € | 222 730,23 € | 236 094,05 € | 250 259,69 € | 265 275,27 € | 281 191,79 € | 2 919 608,82 €
Cash forecast reviewed by adding as hypothesis:
15% contingency on build cost: in order to plan for scope potential evolutions
6% inflation rate starting year 4 (contracts secure prices on 3-4 years arrangements maximum)
35% external costs (could be less / more, it will depend on ABIVAX capacity to deliver)

## Slide 14
 |  |  | Oracle NetSuite |  |  |  |  |  |  |  |  |  |  |  |  | DRAFT - Project Implementation - Timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Project phasing | Project phasing | MILESTONE/ACTIVITIES | WEEKS | 15-Mar |  | 22-Mar | 29-Mar | 5-Apr | 12-Apr | 19-Apr | 26-Apr | 3-May | 10-May | 17-May | 24-May | 31-May | 7-Jun | 14-Jun | 21-Jun | 28-Jun | 5-Jul | 12-Jul | 19-Jul | 26-Jul | 2-Aug | 9-Aug | 16-Aug | 23-Aug | 30-Aug | 6-Sep | 13-Sep | 20-Sep | 27-Sep | 4-Oct | 11-Oct | 18-Oct | 25-Oct | 1-Nov | 8-Nov | 15-Nov | 22-Nov | 29-Nov | 6-Dec | 13-Dec | 20-Dec | 27-Dec | 3-Jan | 10-Jan | 17-Jan
 | Initiate | Initiate | Organisation & Getting Started Sessions |  |  | Prep | Prep | Prep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Personnalization sessions |  |  |  |  | PRS | PRS | PRS | PRS | BRD | BRD | BRD | BRD | BRD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Execute | Execute | Configuration |  |  |  |  |  |  |  |  |  |  |  | CFG | CFG | CFG | CFG | CFG | CFG | CFG | CFG | CFG | CFG | CFG | CFG | CFG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Walkthrough 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | WT1 | WT1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Config Adjustment / Issues adjustment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CFG | CFG | CFG | CFG | CFG | CFG | CFG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Walkthrough 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | WT2 | WT2 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Data Migration |  |  |  |  |  | DM | DM | DM | DM | DM | DM | DM | DM | DM | DM | DM | DM | DM | DM | DM | DM | DM | DMI | DM | SDI | DM | DM | DM | DM | DM | DM | TDI | DM | DM | DM | DM | DM | DM | DM | DM | DM | FDI |  |  |  |  | 
team |  |  | Integrations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | INT | INT | INT | INT | INT | INT | INT | INT |  |  |  |  |  |  |  |  |  | 
 | Validate | Validate | UAT End to End |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UAT | UAT | UAT | UAT |  |  |  |  |  |  |  |  |  | 
 |  |  | Training |  |  |  | TR | TR | TR | TR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TR | TR |  |  |  |  | TR | TR | TR | TR |  |  |  |  |  | 
 | Deploy | Deploy | Go-Live - Cutover |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CO | GL |  |  |  |  | 
 | Improve | Improve | Post Go-Live Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PGL | PGL | PGL | PGL | PGL | PGL
 |  |  | Sponsor (hours / week) |  |  | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4
 |  |  | Project manager (hours / week) |  |  | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 4-8 | 4-8 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8
 |  |  | Administrator (hours / week) |  |  | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4
 |  |  | BPO (hours / week) |  |  | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8 | 4-8 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8+ | 4-8 | 4-8 | 4-8 | 4-8 | 4-8
 |  |  | Key Users |  |  | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 4-8 | 4-8 | 4-8 | 4-8 |  |  |  |  |  |  |  |  |  | 
 |  |  | Data migration owner (hours / week) |  |  | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-5 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4
 |  |  | IT team (hours / week) |  |  | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 4-8 | 0-4 | 0-4 | 0-4 | 0-4 | 0-4
Additional workload cost: The extra workload required from the Finance and IT teams needs to be quantified and costed in order to assess the project’s total cost. Netsuite has provided here a first vision of Abivax workload. Hypothesis could change if we get external support for example.
Comments
Detailed internal workload needed