## Slide 1
ABIVAX
Audit Committee
ERP Controls Readout
March 2026
Audit Committee
Agenda
Current Control Posture
Priority Control Gaps
Target Control Model
Remediation Governance
Audit Committee Ask
CONFIDENTIAL · AUDIT COMMITTEE USE ONLY

## Slide 2
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Overview · Slide 2 of 9
ERP Program Overview
NetSuite selected February 26, 2026 over SAP. Contract execution underway. Program mobilizes April 2026; go-live January 1, 2027.
01
Vendor Selection
NetSuite selected over SAP on February 26, 2026. Key factors: implementation speed (9 months vs. 18+), SaaS-native architecture, proven biotech install base, and total cost advantage. Contract execution underway with prep start targeted March 15, 2026.
02
Implementation Path
Apr 2026: Mobilization — team, blueprint prep, data planning. Apr–Nov 2026: Configure, walkthrough rounds, data migration, integrations, UAT across US and France. Dec 27, 2026: Go-live. Non-negotiable — tied to US public launch Dec 2027.
03
Strategic Purpose
This program is primarily a SOX control-remediation program. NetSuite replaces fragmented manual processes with system-enforced controls across P2P, Audit/Reporting, and period close. Automation efficiency is a Phase 2 objective — after January 1, 2027 go-live.
2 / 9
Audit Committee ERP Controls Readout · March 2026

## Slide 3
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Timeline · Slide 3 of 9
Implementation Timeline
NetSuite implementation: March 15, 2026 prep start → December 27, 2026 go-live → January 17, 2027 post-support complete
Initiation & Design
Configure & Build
Test & Validate
Migration & UAT
GO-LIVE
Mar 15 – Apr 2026
May – Aug 2026
Sep – Oct 2026
Nov – Dec 15, 2026
Dec 27
Pre-Conditions (Mar–Apr)
Contract signed. DoA matrix built (governance pre-req, not ERP task). France vendor master cleanup complete. Blueprint kickoff readiness confirmed.
Internal Resource Requirement
Executive Sponsor: 0–4 hrs/wk. ERP Program Manager: 4–8 hrs/wk. Finance & IT Process Leads: 4–8+ hrs/wk during configure and test phases. NetSuite provides implementation team.
Go-Live Constraints
January 1, 2027 is non-negotiable. December 27, 2026 target preserves buffer. Tied to US public market launch December 2027. Sage 100 decommission follows go-live stabilization.
3 / 9
Audit Committee ERP Controls Readout · March 2026

## Slide 4
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Commercials · Slide 4 of 9
Commercial & Resourcing Model
Year 1 investment estimate ~$1M. Owners: Mike Markman (ERP Lead) + Hema Keshava (CFO/Sponsor). Final contract values pending close of commercial negotiation.
Year 1 Investment View
NetSuite License & Implementation
Subscription + implementation services package. Contract values pending commercial close. ~$1M Year 1 assumption built into budget planning.
Key Integrations (from NetSuite Interfaces XLSX)
Trustpair (vendor validation): API via NS Integration Platform — included in base. Agicap (cash flow): Free SuiteApp. Workiva (reporting): €3,200/yr additional license. All other integrations included in implementation scope.
Year 2+ Assumptions
Annual subscription renewals. Post-go-live optimization and Phase 2 automation investment to be sized separately after January 1, 2027.
Program Ownership & Governance
Internal Program Leads
ERP Program Lead: Mike Markman (VP, Global ERP Lead). Executive Sponsor: Hema Keshava (CFO). Finance Process Lead: Trinidad Mesa (France). IT Lead: TBD. NetSuite provides dedicated implementation PM and functional consultants.
Governance Cadence
Weekly program cadence with milestone-triggered escalations. Monthly executive update to CFO. Board checkpoint at March 19 meeting. Audit Committee briefings at key control decision points.
Note
Commercial package finalization in progress. Final investment figures, detailed SOW, and contract terms will be shared with the Board at the March 19 meeting.
4 / 9
Audit Committee ERP Controls Readout · March 2026

## Slide 5
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Baseline · Slide 1 of 5
Current Control Posture
5 / 9
Audit Committee ERP Controls Readout · March 2026
143
Controls Reviewed (CFTI)
45
Out-of-Scope
60
Ongoing or Design-Phase
9
ERP-Addressable Signals
Manual Process Dependency
Core P2P, reporting, and reconciliation activities remain heavily manual across Sage 100, Trustpair, and Agicap
Control evidence and traceability are inconsistent across systems
IT-dependent manual controls dominate current posture (42 of top automation types)
Vendor Master and Payment Risk
No formal documented review of vendor additions/deletions in Sage 100 (FR-PTP-02G)
Changes to vendor master file not consistently reviewed or approved by Senior GL accountant
Compensating controls exist but are not formalized or evidence-retained
Reporting and Bridge Dependency
39 controls in Reporting/Data Model pillar under review
KPMG-dependent bridge process for French GAAP → IFRS/SEC close cycle
Manual bridging introduces timing and accuracy risk ahead of commercialization
Scalability Risk
Current posture is not scalable for future SEC filing scrutiny
US/France process divergence increases close and control complexity
Legacy design increases key-person and timing dependency risk

## Slide 6
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Gaps · Slide 2 of 5
Priority Control Gaps
6 / 9
Audit Committee ERP Controls Readout · March 2026
Three ERP pillars face distinct control gaps. Each requires owner accountability and ERP-design remediation.
P2P
20 controls in scope
Key Gaps:
Workflow approvals are manual and not system-enforced
Evidence capture fragmented across Sage, Trustpair, Agicap
No automated vendor validation or change monitoring
Payment execution lacks traceability to approval chain
ERP design must:
ERP must enforce approval workflows, centralize vendor master, and create audit trail from PO to payment.
Reporting / Data
39 controls in scope
Key Gaps:
Bridge process is manual and KPMG-dependent each cycle
No multi-entity, multi-GAAP native output capability
Reporting extracts lack dimensional tagging for FP&A
Month-end close is quarterly-paced with manual reconciliation
ERP design must:
ERP must deliver a reporting data model that supports native close, extracts, and reduces consulting dependency.
Controls / Audit
84 controls in scope
Key Gaps:
No single deficiency register with owner and due-date accountability
Control evidence is not retained in a system-managed repository
Integration monitoring and failure escalation paths are undefined
SOD and access controls not consistently designed or tested
ERP design must:
ERP must be designed with control-by-design checkpoints: evidence retention, SOD, and audit trail as non-negotiable.

## Slide 7
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Target · Slide 3 of 5
Target Control Model
7 / 9
Audit Committee ERP Controls Readout · March 2026
The ERP program should be governed as a control-remediation program — not only a technology rollout. These are the design requirements.
01
Embed Approvals and Role Controls In-System
Approval workflows, segregation of duties, and role-based access must be designed into the ERP configuration — not managed through compensating manual controls outside the system.
02
Standardize Feed Ownership and Monitoring
Each data feed, integration, and handoff must have a named owner, defined monitoring step, and documented failure escalation path. No silent failures.
03
Create Traceable Flow: Transaction → Filing
Every transaction must be traceable through approval, processing, and reporting to filing support. Evidence must be system-retained, not manually assembled each cycle.
04
Align Entity Variations Under One Framework
US and France process variants must be rationalized within a common control framework. Divergence must be documented, justified, and bounded — not left to accumulate organically.
Note: France P2P and Reporting/FP&A swimlane process visuals are available in the Process Flows section of the Spine for supporting detail.

## Slide 8
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Remediation · Slide 4 of 5
Remediation Governance
8 / 9
Audit Committee ERP Controls Readout · March 2026
A dated remediation program is required now — not post-selection. ERP milestones must tie to control-closure checkpoints.
Single Deficiency Register
One authoritative register with severity, owner, due date, and status. No parallel lists. Eliminates 'which version is current?' ambiguity.
Weekly Remediation Governance
Weekly workstream cadence with monthly audit committee rollup. Owner-dated updates required; no status without evidence.
ERP Milestones → Control Checkpoints
Key ERP design and blueprint milestones are tied to control-closure deliverables. Can't advance phase without closed evidence.
Escalation Protocol
Slippage against critical control deficiencies triggers defined escalation. Audit committee notified monthly on at-risk items.

## Slide 9
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Ask · Slide 5 of 5
Audit Committee Ask
9 / 9
Audit Committee ERP Controls Readout · March 2026
01
Endorse Control-By-Design as Non-Negotiable ERP Principle
Confirm that system-enforced controls, evidence retention, and SOD design are foundational ERP requirements — not post-implementation add-ons.
Audit Cmte
02
Require Owner/Date Accountability on Priority Control Gaps
Direct that each CFTI-registered control gap has a named owner, dated remediation commitment, and visible status before ERP blueprint begins.
Finance / IT
03
Approve Monthly Remediation Reporting Cadence
Formally approve the format and frequency: weekly governance, monthly audit committee update with at-risk escalation and evidence-based status.
Audit Cmte / Mike
04
Authorize Fast-Track Support on Controls That Threaten Timeline
Grant authority to escalate resource constraints or decision delays that put critical control-closure checkpoints at risk ahead of Jan 1, 2027 go-live.
Audit Cmte / Hema
Slides due: March 6, 2026 · Meeting: March 2026 (date TBD with Camille) · Owner: Mike Markman