## Cover page
Abivax financial grids
Support in choosing and implementing an ERP solution

## Cash forecast analysis
Hypothesis used for final comparison (%)
Contingency | 15%
Inflation rate for licenses costs and TMA - from Y4 | 6%
External support % | 35%
Additional costs in analysis (comparison cash conso forecast VS cash forecast analysis
|  | Netsuite - Oracle | SAP - KPMG |  | Netsuite - Oracle | SAP - KPMG | Comment | [5 empty] | Differences
Overall cost over 3 years |  | 1238305.8 | 2172714.9528 |  | 333734.8 | 588772.6509 | Contingency + external support
Overall cost over 5 years |  | 1646657.779 | 2649482.1768 |  | 440052.779 | 720373.8749 | Contingency + external support + inflation rate
Overall cost over 10 years |  | 2902208.8172 | 4115388.096 |  | 940518.8172 | 1323364.7942 | Contingency + external support + inflation rate
Sub-total “Run” Saas (3 years) |  | 561025.8 | 573425 |  | 107974.8 | 55676 | No inflation rate
Sub-total “Run” Saas (5 years) |  | 969377.779 | 1050192.224 |  | 214292.779 | 187277.224 | Inflation rate - because of transitional year for the MS program and reduction of costs environment
Sub-total “Run” Saas (10 years) |  | 2224928.8172 | 2516098.1432 |  | 714758.8172 | 790268.1432 | Inflation rate
After first negociations
Cash-out forecast for Abivax
Editor/Implementer |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | TOTAL |  | CTRL
Netsuite - Oracle | Build + T&E + Contingency | 519248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 519248 |  | 0
| External support | 158032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158032 |  | 0
| Run (license cost and TMA) | 187008.6 | 187008.6 | 187008.6 | 198229.116 | 210122.863 | 222730.2347 | 236094.0488 | 250259.6918 | 265275.2733 | 281191.7897 | 2224928.8172
| TOTAL | 864288.6 | 187008.6 | 187008.6 | 198229.116 | 210122.863 | 222730.2347 | 236094.0488 | 250259.6918 | 265275.2733 | 281191.7897 | 2902208.8172
SAP - KPMG | Build + T&E + Contingency | 904128.0472 | 321994.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226122.2972 |  | 0
| External support | 275169.4057 | 97998.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373167.6557 |  | 0
| Run (license cost and TMA) | 136745 | 218340 | 218340 | 231440.4 | 245326.824 | 260046.4334 | 275649.2194 | 292188.1726 | 309719.463 | 328302.6307 | 2516098.1432
| TOTAL | 1316042.4528 | 638332.5 | 218340 | 231440.4 | 245326.824 | 260046.4334 | 275649.2194 | 292188.1726 | 309719.463 | 328302.6307 | 4115388.096

## Cash forecast consolidation
Cash-out forecast for Abivax
Editor/Implementer |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | CTRL | CTRL
Netsuite - Oracle | BUILD | 451520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Run & TMA | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 0 | 0
| TOTAL | 638528.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6
SAP - KPMG | BUILD | 786198.3019 | 279995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Run & TMA | 136745 | 218340 | 218340 | 218340 | 218340 | 218340 | 218340 | 218340 | 218340 | 218340 | 0 | -81595 | -81K OK reated to Y1 ramp up
| TOTAL | 922943.3019 | 498335 | 218340 | 218340 | 218340 | 218340 | 218340 | 218340 | 218340 | 218340
Consolidation of the offers sent by applicants - with no additions from KPMG choice assistance team

## Financial analysis conso
DETAIL OF FINANCIAL ANALYSIS
|  | Netsuite - Oracle | SAP - KPMG
Saas
Overall cost over 3 years |  | 904571 | 1583942.3019
Overall cost over 5 years |  | 1206605 | 1929108.3019
Overall cost over 10 years |  | 1961690 | 2792023.3019
Build | Project management | 20960 | 146700
| Initialization | 50640 | 5800
| Solution design | 16440 | 114410
| Solution implementation | 269240 | 246408.3019
| Data recovery | 17120 | 0
| Acceptance | 11360 | 84100
| Training | 13920 | 0
| Production start-up and assistance | 15760 | 109680
| Maintenance and user support during the warranty phase | 0 | 0
| Reversibility management | 6640 | 0
| Best-of-breed implementation (options) | 11440 | 341095
| Travel expenses | 18000 | 18000
| Sub-total “Build” (One-Off) | 451520 | 1066193.3019
Run | SAAS rent (annual) | 109908 | 115333
| SaaS rent (annual unit basis) | 779.4894 | 348.4381
| SaaS rent (monthly basis) | 9159 | 13424.1667
| SaaS rent (annual basis) | 109908 | 115333
| Best of Breed SaaS rent (annual basis) | 23935.8 | 45757
| Hosting subscription (annual) | 0 | 0
| Other costs | 12055.8 | 0
| TMA (annual) | 41109 | 57250
| Support (annual basis) | 21257.4 | 14400
| TMA rent (annual basis) | 19851.6 | 42850
| Other support / maintenance services | 0 | 0
| Sub-total “Run” Saas (annual) | 151017 | 172583
| Sub-total “Run” Saas (5 years) | 755085 | 862915
Total (man days) |  | 372 | 747.5
Integrator's average daily rate |  | 1165.3763 | 1402.2653
Abivax Workload |  | 134 | 480
Ratio Abivax load VS implementer |  | 0.36022 | 0.64214
Consolidation of the offers sent by applicants - with no additions from KPMG choice assistance team
Note on C21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4 to 6 weeks post-Go-Live
Note on D21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 mois d'hypercare

## Financial analysis With BoB
DETAIL OF FINANCIAL ANALYSIS
|  | Netsuite - Oracle | SAP - KPMG
Saas
Overall cost over 3 years |  | 1012545.8 | 1721213.3019
Overall cost over 5 years |  | 1386563 | 2157893.3019
Overall cost over 10 years |  | 2321606 | 3249593.3019
Build | Project management | 20960 | 146700
| Initialization | 50640 | 5800
| Solution design | 16440 | 114410
| Solution implementation | 269240 | 246408.3019
| Data recovery | 17120 | 0
| Acceptance | 11360 | 84100
| Training | 13920 | 0
| Production start-up and assistance | 15760 | 109680 | 2 hypercare months for SAP
| Maintenance and user support during the warranty phase | 0 | 0
| Reversibility management | 6640 | 0
| Best-of-breed implementation (options) | 11440 | 341095
| Travel expenses | 18000 | 18000
| Sub-total “Build” (One-Off) | 451520 | 1066193.3019
Run | SAAS rent (annual) | 145899.6 | 161090
| SaaS rent (annual unit basis) | 779.4894 | 348.4381
| SaaS rent (monthly basis) | 9159 | 13424.1667
| SaaS rent (annual basis) | 109908 | 115333
| Best of Breed SaaS rent (annual basis) | 23935.8 | 45757
| Hosting subscription (annual) | 0 | 0
| Other costs | 12055.8 | 0
| TMA (annual) | 41109 | 57250
| Support (annual basis) | 21257.4 | 14400
| TMA rent (annual basis) | 19851.6 | 42850
| Other support / maintenance services | 0 | 0
| Sub-total “Run” Saas (annual) | 187008.6 | 218340
| Sub-total “Run” Saas (5 years) | 935043 | 1091700
Total (man days) without best of breed |  | 382 | 1075.875
Integrator's average daily rate |  | 1134.8691 | 974.2705
Abivax Workload |  | 134 | 480
Ratio Abivax load VS inmplementer |  | 0.35079 | 0.44615
Consolidation of the offers sent by applicants - with no additions from KPMG choice assistance team
Note on C21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4 to 6 weeks post-Go-Live
Note on D21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 mois d'hypercare
Note on E21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Ben Alaya, Aymen peux-tu vérifier dans les offres si la durée de l’hypercare est mentionnée Reply: Done, je les ai ajouté en commentaire

## Graph
| BUILD (3) | BUILD (4)
| Netsuite - Oracle | SAP - KPMG
Project management | 18 | 144
Initialization | 46 | 4
Solution design | 15 | 109.5
Total design | 61 | 113.5
Solution implementation | 235 | 296
Data recovery | 16 | 0
Acceptance | 10 | 94
Training | 12 | 0
Production start-up and assistance | 14 | 100
Maintenance and user support during the warranty phase | 0 | 0
Reversibility management | 6 | 0
| 372 | 747.5

## License price analysis
| Netsuite - Oracle | SAP - KPMG
Unit public price per user per year for Core solution for a full user | 1097.8723 | 812.2042
Discount proposed on public price | 29% | Not communicated
Unit price per user per year for Core solution for a full user | 779.4894 | 812.2042
License mix | NetSuite SuiteSuccess Financials Premium Cloud Service: 1 for 43K each NetSuite General Access Cloud Service User (full user): 42 for 1K3 each NetSuite Employee Self-Serve Cloud Service Users: 85 for 216 each NetSuite Specialized View and Approve Cloud Service Users: 10 for 336 each NetSuite OneWorld Cloud Service: 1 for 21,6K each NetSuite Procurement Mid-Market Cloud Service: 1 for 6K480 each NetSuite Inventory Management Mid-Market Cloud Service: 1 for 6k480 each | SAP Finance and Supply Chain developer: 2 for 2K9 each SAP Finance Base: 15 for 3K each SAP Finance and Supply Chain operations: 35 for 700 each SAP Finance and Supply Chain self-service: 90 for 146 each SAP Ariba Central Invoice Management: 20 for 618 each SAP AI Units: 10 for 320 each SAP BTPEA - Build Automation: 1 for 11K each
Total amount of licenses for Core solution / per year | 141 | 142
Total amounts of licenses per year discounts included / with best of breed solution | 133843.8 | 161090
Total amount / by number of real Abivax users (142 in RFP) | 942.562 | 1134.4366
|  |  | #REF! | #REF! | #DIV/0! | #DIV/0!

## Best of breed
| Netsuite - Oracle | SAP - KPMG
Best-of-breed implementation nb of days | 10 | 328.375

## RUN (3)
|  |  | Company name | Oracle Corporation UK Limited
|  |  | Solution name | Netsuite
DETAIL OF RUN
Fields to be completed by applicant
License cost
| Criteria | Quantity | Unit price by year by user | Acquisition cost Public price | Applicable rebate | Final offer V1 | Comments
| Licences Core Model | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax
| NetSuite SuiteSuccess Financials Premium Cloud Service | 1 | 43080 | 43080 | 29% | 30586.8 | This refers to the core ERP, which includes all standard functionalities, excluding optional modules.
| NetSuite General Access Cloud Service User (full user) | 42 | 1320 | 55440 | 29% | 39362.4 | This represents the upper-bound assumption for the number of Full users. This number can be reduced in favor of “Self-Serve” or “View and Approve” user profiles, following our discussions to define the appropriate user volume based on business needs.
| NetSuite Employee Self-Serve Cloud Service Users | 85 | 216 | 18360 | 29% | 13035.6 | The NetSuite Employee Self-Serve user is a limited-access internal user designed for employees to perform basic self-service activities. This user profile allows employees to: Enter and submit their worked time Submit personal expense reports Submit purchase requests Create and submit support tickets Approve time and expense transactions Create events, contacts, and tasks in the NetSuite calendar This role does not provide any access to accounting, financial, sales, administrative, or marketing functions, nor to financial reports, budgets, or transactions (including view-only access). - One pack of 5 NetSuite Employee Self-Service Cloud Service Users is already included in the NetSuite SuiteSuccess Financials Premier core ERP.
| NetSuite Specialized View and Approve Cloud Service Users | 10 | 336 | 3360 | 29% | 2385.6 | NetSuite Specialized View and Approve Cloud Service 5-Pk Users allows a User to have read-only access and approve specific records, as listed below, within the NetSuite Cloud Service. • Invoices; • Journal Entries; • Return Authorizations; • Sales Orders; • Transfer Orders; • Vendor Bills; • Vendor Payments; • Vendor In-Transit Payments; and • Vendor Return Authorizations. If Customer has Procurement Management Cloud Service (any edition), then NetSuite Specialized View and Approve Cloud Service 5-Pk Users allows a User to have read-only access and approve specific records, as listed below: • Blanket Purchase Orders; • Purchase Contract Approvals; and • Requisitions Approvals. NetSuite Specialized View and Approve Cloud Service 5-Pk Users cannot: • Transact within the NetSuite Service; • Set up or configure any NetSuite Service; • Modify pre-established permissions already restricted to “Approve” or “View-Only” access; • View payroll information; or • View employee records. Usage Limits: NetSuite Specialized View and Approve Cloud Service 5-Pk Users is subject to the following usage limits: • Customer is entitled to the quantity of NetSuite Specialized View and Approve Cloud Service 5-Pk Users specified in Customer’s Estimate Order Form. • NetSuite Specialized View and Approve Cloud Service 5-Pk Users is limited to only the features and functionalities and Customer records listed above that the Customer makes available to the specific NetSuite Specialized View and Approve Cloud Service 5-Pk Users. If customizations result in modifications to the access and use rights granted to the NetSuite Specialized View and Approve Cloud
| NetSuite OneWorld Cloud Service | 1 | 21600 | 21600 | 29% | 15336 | NetSuite OneWorld allows a company to manage multiple subsidiaries, business units, and locations across different countries, including localized operations like US subsidiaries.
| NetSuite Procurement Mid-Market Cloud Service | 1 | 6480 | 6480 | 29% | 4600.8
| NetSuite Inventory Management Mid-Market Cloud Service | 1 | 6480 | 6480 | 29% | 4600.8
| Sub-total for licences cost (core model exc. Best of breed) | 141 | 79512 | 154800 |  | 109908
| Add-ons, best-of-breed and other licenses by domain | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax
| NetSuite Analytics Warehouse Standard Cloud Service (NSAW) | 1 | 8160 | 8160 | 29% | 5793.6 | NetSuite Analytics Warehouse (NSAW) is NetSuite’s BI tool for reporting, analytics, and dashboards. 10 users included
| Oracle Integration Cloud Service for Oracle SaaS - Standard (NSIP) | 1 | 6720 | 6720 | 29% | 4771.2 | NSIP is NetSuite’s ETL tool for integrating, transforming, and syncing data
| ZoneCapture | 1 | 6555 | 6555 |  | 6555 | Partner solution (SDN) built for NetSuite for OCR. Pricing is based on the number of vendor invoices. The indicated price corresponds to a maximum volume of 500 invoices per month.
Moved from "Other cost items | NetSuite Electronic Invoices Mid-Market Cloud Service | 1 | 8640 | 8640 | 29% | 6134.4 | This service supports e-invoicing by enabling the creation, transmission, and management of electronic invoices directly within NetSuite.
Moved from "Other cost items | NetSuite Electronic Business Extension | 1 | 240 | 240 | 29% | 170.4 | NetSuite Electronic Business Extension provides the secure integration layer required to enable electronic business communications, including e-invoicing, between NetSuite and external partners or networks.
Moved from "Other cost items | NetSuite Electronic Document Processing Cloud Service | 1 | 720 | 720 | 29% | 511.2 | NetSuite Electronic Document Processing Cloud Service enables the electronic processing of various business documents (such as invoices, bills, credit memos, cash sales, purchase orders, and more) through Avalara networks, with each license including a cap of 1000 Documents Processed per 12-month period.
| Sub-total for licences cost (Best of breed) | 6 | 31035 | 31035 |  | 23935.8
| Support & Maintenance | Quantity | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax
| Support (helpdesk) = 20 days per year NetSuite Premium Support | 1 | 16980 | 16980 | 29% | 12055.8
| Maintenance : • Corrective maintenance = 30 days per year • Major release assistance = 10 days per year • Evolution assistance = 15 days a year • Project management related to the follow-up of services provided = 2 hours by quarter | 1 | 27960 | 27960 | 29% | 19851.6 | refer to appendix ABIVAX - Appendix Delivery team NetSuite CS.zip document in 008 Maintenance team - ACS presentation
| Customer Learning Cloud Support Company Pass - Premium | 1 | 12960 | 12960 | 29% | 9201.6
| Total other services offered | 3 | 57900 | 57900 |  | 41109
| Other cost items (infrastructure, etc.) | Quantity | Unit price € Excluding tax | € Excluding tax | % | € Excluding tax
| Hosting subscription (annual) |  |  | 0 |  | 0
| NetSuite Standard Tier Infrastructure Cloud Service (included) | 1 |  | 0 | 29% | 0 | Standard Tier – Infrastructure sized according to transaction volume and user count; to be confirmed based on discussions. This is the Standard version, which can be upgraded to premium based on our discussions.
| NetSuite Sandbox Environment Cloud Service | 1 | 16980 | 16980 | 29% | 12055.8
| Sub-total for other items | 2 | 16980 | 16980 |  | 12055.8
|  | TOTAL |  |  |  | 187008.6
It is understood that further discussions and dialogue will take place between us and that these may lead us to agree changes to the solution which is currently envisaged. If that happens we will issue an updated estimate reflecting such changes.

## BUILD (3)
|  | Company name | Oracle Corporation UK Limited
|  | Solution name | Netsuite
DETAIL OF BUILD
Is the project costed on a fixed-price basis?
Fields to be completed by applicant
Phases | Workloads Provider / profile / phase | [9 empty] | GC workloads / profile / phase | [7 empty] | Assumptions / Comments
| Project Director Profile | Project Manager Profile | Technical Consultant Profile | Functional Consultant Profile | Trainer Profile | IT Architect Profile | Profile xxxxxx | Profile xxxxxx | Total (Days) | Total € by phase | Project Manager | BPO | Key User | Users | IT team member (technical responsible) | Profile xxxxxx | Profile xxxxxx | Total (D) | Total € by phase
Average daily rate by profile (in € excl. tax) | 1240 | 1160 | 1000 | 1160 | 1160 | 1160
| Estimated workload (in days) | [9 empty] | Estimated workload (in days)
Project management | 3 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 20960 | 5 | 2 | 1 | 0 | 1 | 0 | 0 | 9
Project follow-up | 3 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 20960 | 5 | 2 | 1 | 0 | 1 |  |  | 9
Initialization | 2 | 6 | 18 | 16 | 0 | 4 | 0 | 0 | 46 | 50640 | 8 | 9 | 7 | 0 | 6 | 0 | 0 | 30
Project scoping and launch | 2 | 6 | 2 | 0 | 0 | 1 | 0 |  | 11 | 12600 | 4 | 2 | 1 | 0 | 1 |  |  | 8
Technical analysis | 0 | 0 | 1 | 7 | 0 | 2 | 0 |  | 10 | 11440 | 1 | 1 | 1 | 0 | 2 |  |  | 5
Functional analysis | 0 | 0 | 11 | 4 | 0 | 1 | 0 |  | 16 | 16800 | 2 | 4 | 3 | 0 | 1 |  |  | 10
Data analysis | 0 | 0 | 2 | 3 | 0 | 0 | 0 |  | 5 | 5480 | 1 | 2 | 1 | 0 | 1 |  |  | 5
Preparation of environments | 0 | 0 | 2 | 2 | 0 | 0 | 0 |  | 4 | 4320 | 0 | 0 | 1 | 0 | 1 |  |  | 2
Solution design | 0 | 0 | 6 | 9 | 0 | 0 | 0 | 0 | 15 | 16440 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 6
Drafting of solution design file | 0 | 0 | 3 | 6 | 0 | 0 | 0 |  | 9 | 9960 | 1 | 2 | 1 | 0 | 0 |  |  | 4
Definition of development plan | 0 | 0 | 3 | 3 | 0 | 0 | 0 |  | 6 | 6480 | 1 | 1 | 0 | 0 | 0 |  |  | 2
Initialization and design | 2 | 6 | 24 | 25 | 0 | 4 | 0 | 0 | 61 | 67080 | 10 | 12 | 8 | 0 | 6 | 0 | 0 | 36
Solution implementation | 0 | 0 | 21 | 208 | 0 | 6 | 0 | 0 | 235 | 269240 | 0 | 7 | 10 | 1 | 9 | 0 | 0 | 27
Specific development and parameterization | 0 | 0 | 9 | 139 | 0 | 2 | 0 |  | 150 | 172560 | 0 | 2 | 2 | 0 | 2 |  |  | 6
Realization of interfaces (please provide with the details in the Interfaces detail tab) | 0 | 0 | 5 | 49 | 0 | 1 | 0 |  | 55 | 63000 | 0 | 0 | 0 | 0 | 3 |  |  | 3
Production of editions | 0 | 0 | 1 | 7 | 0 | 0 |  |  | 8 | 9120 | 0 | 1 | 1 | 0 | 1 |  |  | 3
Production of indicators and dashboards | 0 | 0 | 2 | 5 | 0 | 1 |  |  | 8 | 8960 | 0 | 1 | 2 | 0 | 1 |  |  | 4
Unit testing | 0 | 0 | 2 | 5 | 0 | 1 |  |  | 8 | 8960 | 0 | 1 | 2 | 0 | 1 |  |  | 4
End-to-end testing support | 0 | 0 | 2 | 3 | 0 | 1 |  |  | 6 | 6640 | 0 | 2 | 3 | 1 | 1 |  |  | 7
Data migration | 0 | 0 | 9 | 6 | 0 | 1 | 0 | 0 | 16 | 17120 | 2 | 6 | 1 | 0 | 5 | 0 | 0 | 14
Cleaning and standardization of repositories | 0 | 0 | 3 | 0 | 0 | 0 |  |  | 3 | 3000 | 0 | 2 | 0 | 0 | 2 |  |  | 4
Formalization of target data architecture | 0 | 0 | 2 | 3 | 0 | 1 |  |  | 6 | 6640 | 1 | 2 | 0 | 0 | 1 |  |  | 4
Data migration | 0 | 0 | 4 | 3 | 0 | 0 |  |  | 7 | 7480 | 1 | 2 | 1 | 0 | 2 |  |  | 6
Acceptance | 1 | 4 | 2 | 2 | 0 | 1 | 0 | 0 | 10 | 11360 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 5
Support during acceptance phase | 1 | 4 | 2 | 2 | 0 | 1 |  |  | 10 | 11360 | 0 | 1 | 2 | 2 | 0 |  |  | 5
Training | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 13920 | 1 | 8 | 7 | 6 | 2 | 0 | 0 | 24
Formalization of training plan and training materials (for users, tool admins and managers) | 0 | 0 | 0 | 0 | 6 |  |  |  | 6 | 6960 | 1 | 2 | 1 |  |  |  |  | 4
Conduct training sessions (for users, tool admins and managers) | 0 | 0 | 0 | 0 | 6 |  |  |  | 6 | 6960 |  | 6 | 6 | 6 | 2 |  |  | 20
Production start-up and assistance | 0 | 4 | 3 | 5 | 0 | 2 | 0 | 0 | 14 | 15760 | 3 | 2 | 2 | 1 | 2 | 0 | 0 | 10
Decommissioning and changeover | 0 | 2 | 1 | 2 | 0 | 1 |  |  | 6 | 6800 | 1 | 1 | 0 | 0 | 1 |  |  | 3
Production start-up and assistance | 0 | 2 | 2 | 3 | 0 | 1 |  |  | 8 | 8960 | 2 | 1 | 2 | 1 | 1 |  |  | 7
Maintenance and user support during the warranty phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 2 | 0 | 0 | 6
Maintenance and user support | [8 empty] | 0 | 0 | 1 | 2 | 1 |  | 2 |  |  | 6 | ACS support included in the Run section
Reversibility management | 0 | 1 | 2 | 2 | 0 | 1 | 0 | 0 | 6 | 6640 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 3
Reversibility management | 0 | 1 | 2 | 2 |  | 1 |  |  | 6 | 6640 | 1 |  |  |  | 2 |  |  | 3
Best of breed implementation (only total amounts for each best of breed solution - you can copy this tab to make a separate financial grid for each solution) | 0 | 1 | 1 | 8 | 0 | 0 | 0 | 0 | 10 | 11440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Best of breed 1 - NSAW (NetSuite Analytics DataWarehouse) Total | 0 | 1 | 1 | 8 | 0 | 0 | 0 | 0 | 10 | 11440 | [7 empty] | 0 | NSAW configuration included in the core project (around 100 hours)
Best of breed 2 - Zone Capture (OCR) - Standard implementation - Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
Best of breed 3 Total | [8 empty] | 0 | 0 | [7 empty] | 0
Total Implementation (D) | 6 | 30 | 63 | 256 | 12 | 15 | 0 | 0 | 382 | 433520 | 23 | 40 | 32 | 10 | 29 | 0 | 0 | 134
Travel expenses | 18000
COST PER PROFILE ( € ) excl. tax (for the domain) / incl. Travel expenses | 7440 | 34800 | 63000 | 296960 | 13920 | 17400 | 0 | 0
TOTAL COST ( € ) excl. tax for the domain | 451520
Average daily rate | 1134.8691
It is understood that further discussions and dialogue will take place between us and that these may lead us to agree changes to the solution which is currently envisaged. If that happens we will issue an updated estimate reflecting such changes.

## Netsuite Interface details
|  | Company name | Oracle Corporation UK Limited
|  | Solution name | Netsuite
INTERFACES DETAILS
Fields to be completed by applicant
ID | No. | Application name (t obe interfaced with the future ERP system | Business objects exchanged | Estimation in number of days
Interfaces with existing solutions
001 | 1 | Trust Pair | Supplier database verification (vendor master data, risk scoring, validation status) | 5
002 | 2 | Agicap | Treasury & cash management (cash positions, bank transactions, forecasts) | 3
003 | 3 | E-invoicing platform (TBD) | E-invoicing management (customer & supplier invoices, statuses, legal archiving references) | 3
004 | 4 | ADP | Payroll data, HR master data | 4
005 | 5 | Lucca | People management | 3
006 | 6 | Workday Adaptive Planning | Budget data, forecasts, analytical structures | 8
007 | 7 | Workiva | Financial reporting data (journals, adjustments, disclosure items) | 6
008 | 8 | SAP Concur | Expense report | 2
Interfaces with possible future solutions
009 | 9 | 3PL | Inventory, shipment, and logistics data | 12
010 | 10 | Order to cash partner | Order-to-cash information, including orders, billing, and customer transactions | 8
011 | 11 | Production partner | Production data such as manufacturing orders, consumption, and outputs with the production system. | 8

## Netsuite Cash forecast
|  | Company name | Oracle Corporation UK Limited
|  | Solution name | Netsuite
DETAIL OF CASH FORECAST
Cash-out forecast for Abivax
Cash-out forecast for Abivax | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Build | 451520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451520
Run (license cost and TMA) | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 187008.6 | 1870086
It is understood that further discussions and dialogue will take place between us and that these may lead us to agree changes to the solution which is currently envisaged. If that happens we will issue an updated estimate reflecting such changes.
NB : KPMG a retiré le taux d'inflation de 7% car il est déjà comptabilisé dans l'analyse générale
Please use assumptions for roll-out detailed in the RFP main document.
Please use assumptions for roll-out detailed in the RFP main document.

## Netsuite Financial analysis
L
| Company name | Oracle Corporation UK Limited
| Solution name | Netsuite
DETAIL OF FINANCIAL ANALYSIS
ERP solution - Integrator
Saas
Overall cost over 3 years |  | 1012545.8
Overall cost over 5 years |  | 1386563
Overall cost over 10 years |  | 2321606
Build | Project management | 20960
| Initialization | 50640
| Solution design | 16440
| Solution implementation | 269240
| Data recovery | 17120
| Acceptance | 11360
| Training | 13920
| Production start-up and assistance | 15760
| Maintenance and user support during the warranty phase | 0
| Reversibility management | 6640
| Best-of-breed implementation | 11440
| Travel expenses | 18000
| Sub-total “Build” (One-Off) | 451520
Run | SAAS rent (annual) | 145899.6
| SaaS rent (annual unit basis) | 779.4894
| SaaS rent (monthly basis) | 9159
| SaaS rent (annual basis) | 109908
| Best of Breed SaaS rent (annual basis) | 23935.8
| Hosting subscription (annual) | 0
| Other costs | 12055.8
| TMA (annual) | 41109
| Support (annual basis) | 21257.4
| TMA rent (annual basis) | 19851.6
Other support / maintenance services
| Sub-total “Run” Saas (annual) | 187008.6
| Sub-total “Run” Saas (5 years) | 935043
Total (man days) |  | 382
Integrator's average daily rate |  | 1134.8691
Abivax Workload |  | 134
It is understood that further discussions and dialogue will take place between us and that these may lead us to agree changes to the solution which is currently envisaged. If that happens we will issue an updated estimate reflecting such changes.

## RUN (4)
|  | Company name | KPMG
|  | Solution name | SAP S/4HANA Public Cloud
DETAIL OF RUN
Fields to be completed by applicant
License cost
Criteria | Quantity | Unit price by year by user | Acquisition cost Public price | Applicable rebate | Final offer V1 | Comments
Licences Core Model | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax
SAP Finance and Supply Chain developer | 2 | 2928 | 5856 |  | 5856
SAP Finance Base | 15 | 3045.1333 | 45677 |  | 45677
SAP Finance and Supply Chain operations | 35 | 688.0857 | 24083 |  | 24083
SAP Finance and Supply Chain self-service | 90 | 146.4 | 13176 |  | 13176
SAP Ariba Central Invoice Management | 20.0081 | 618 | 12365 |  | 12365
SAP AI Units | 9.9875 | 320 | 3196 |  | 3196
SAP BTPEA - Build Automation | 1 | 10980 | 10980 |  | 10980
Sub-total for licences cost (core model exc. Best of breed) | 142 | 18725.619 | 115333 |  | 115333
Add-ons, best-of-breed and other licenses by domain | 1899-12-31 | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax
SAP Document and Reporting Compliance (Recommended) | 1 | 4488 | 4488 |  | 4488 | Optional? To be checked in SAP doc
Cloud Edition (Recommended) | 1 | 4411 | 4411 |  | 4411 | Optional? To be checked in SAP doc
SAP intergration Suite, basic edition (Recommended) | 1 | 17185 | 17185 |  | 17185 | Optional? To be checked in SAP doc
Customer-Managed Data Products | 1 | 11814 | 11814 |  | 11814 | Optional? To be checked in SAP doc
SAP Business Data Cloud, core capacity | 1 | 5060 | 5060 |  | 5060 | Optional? To be checked in SAP doc
WalkMe LearningArc | 140 | 19.9929 | 2799 |  | 2799 | Optional? To be checked in SAP doc
|  |  | 0 |  | 0
|  |  | 0 |  | 0
Sub-total for licences cost (Best of breed) | 140 | 42977.9929 | 45757 |  | 45757
Support & Maintenance | Day | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax
Support (helpdesk) = 20 days per year | 20 | 720 | 14400 |  | 14400
Maintenance : • Corrective maintenance = 30 days per year • Major release assistance = 10 days per year • Evolution assistance = 15 days a year • Project management related to the follow-up of services provided = 2 hours by quarter | 55 | 779.0909 | 42850 |  | 42850
List other services offered |  |  | 0 |  | 0
List other services offered |  |  | 0 |  | 0
Total other services offered | 75 | 1499.0909 | 57250 |  | 57250
Other cost items (infrastructure, etc.) | Quantity | Unit price € Excluding tax | € Excluding tax | % | € Excluding tax
Hosting subscription (annual) |  |  | 0 |  | 0
List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0
List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0
List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0
Sub-total for other items | 0 | 0 | 0 |  | 0
| TOTAL |  |  |  | 218340
Note on H22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: E-invoicing solution
Note on H24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Middleware solution
Note on H26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A unified dara platform for better BI capabilities
Note on H27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Optional : An integrated digital adoption solution to provide step-by-step user guidance, accelerating software onboarding and reducing data entry errors through live on-screen interactive assistance.

## BUILD (4)
|  | Company name | KPMG
|  | Solution name | SAP S/4HANA Public Cloud
DETAIL OF BUILD
Is the project costed on a fixed-price basis?
Fields to be completed by applicant
Phases | Workloads Provider / profile / phase | [9 empty] | GC workloads / profile / phase | [7 empty] | Assumptions / Comments
| Project Director Profile | Project Manager Profile | Technical Consultant Profile | Functional Consultant Profile | Trainer Profile | IT Architect Profile | Profile xxxxxx | Profile xxxxxx | Total (Days) | Total € by phase | Project Manager | BPO | Key User | Users | IT team member (technical responsible) | Profile xxxxxx | Profile xxxxxx | Total (D) | Total € by phase
Average daily rate by profile (in € excl. tax) | 1800 | 1100 | 850 | 1500 | 780 | 1300 | 520 | 520
| Estimated workload (in days) | [9 empty] | Estimated workload (in days)
Project management | 9 | 63 | 72 | 0 | 0 | 0 | 0 | 0 | 144 | 146700 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 60
Project follow-up | 9 | 63 | 72 | [5 empty] | 144 | 146700 | 60 | [6 empty] | 60
Initialization | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 4 | 5800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project scoping and launch |  |  |  | 3 |  | 0.5 |  |  | 3.5 | 5150 | [7 empty] | 0
Technical analysis | [8 empty] | 0 | 0 | [7 empty] | 0
Functional analysis | [8 empty] | 0 | 0 | [7 empty] | 0
Data analysis | [8 empty] | 0 | 0 | [7 empty] | 0
Preparation of environments | [5 empty] | 0.5 |  |  | 0.5 | 650 | [7 empty] | 0
Solution design | 0 | 0 | 0 | 34.5 | 59.5 | 10.5 | 5 | 0 | 109.5 | 114410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drafting of solution design file |  |  |  | 34.5 | 59.5 | 10.5 | 5 |  | 109.5 | 114410 | [7 empty] | 0
Definition of development plan | [8 empty] | 0 | 0 | [7 empty] | 0
Initialization and design | 0 | 0 | 0 | 37.5 | 59.5 | 11.5 | 5 | 0 | 113.5 | 120210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solution implementation | 0 | 0 | 0 | 59.4906 | 119.4906 | 4 | 83.0189 | 30 | 296 | 246408.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Specific development and parameterization |  |  |  | 35 | 95 | 4 | 14 | 30 | 178 | 154680 | [7 empty] | 0
Realization of interfaces (please provide with the details in the Interfaces detail tab) |  |  |  | 24.4906 | 24.4906 |  | 69.0189 |  | 118 | 91728.3019 | [7 empty] | 0
Production of editions | [8 empty] | 0 | 0 | [7 empty] | 0
Production of indicators and dashboards | [8 empty] | 0 | 0 | [7 empty] | 0
Unit testing | [8 empty] | 0 | 0 | [7 empty] | 0
End-to-end testing support | [8 empty] | 0 | 0 | [7 empty] | 0
Data migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cleaning and standardization of repositories | [8 empty] | 0 | 0 | [7 empty] | 0
Formalization of target data architecture | [8 empty] | 0 | 0 | [7 empty] | 0
Data migration | [8 empty] | 0 | 0 | [7 empty] | 0
Acceptance | 0 | 0 | 0 | 24 | 45 | 0 | 5 | 20 | 94 | 84100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Support during acceptance phase |  |  |  | 24 | 45 |  | 5 | 20 | 94 | 84100 | [7 empty] | 0
Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formalization of training plan and training materials (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0
Conduct training sessions (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0
Production start-up and assistance | 0 | 0 | 0 | 44 | 56 | 0 | 0 | 0 | 100 | 109680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decommissioning and changeover | [8 empty] | 0 | 0 | [7 empty] | 0
Production start-up and assistance |  |  |  | 44 | 56 |  |  |  | 100 | 109680 | [7 empty] | 0
Maintenance and user support during the warranty phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maintenance and user support | [8 empty] | 0 | 0 | [7 empty] | 0
Reversibility management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reversibility management | [8 empty] | 0 | 0 | [7 empty] | 0
Best of breed implementation (only total amounts for each best of breed solution - you can copy this tab to make a separate financial grid for each solution) | 0 | 38 | 0 | 49.25 | 75 | 103.25 | 62.875 | 0 | 328.375 | 341095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Best of breed 1 Total (Middleware) | [5 empty] | 47 |  |  | 47 | 61100 | [7 empty] | 0
Best of breed 2 Total (eletronic invoicing) |  | 38 |  | 49.25 | 75 | 37.25 | 62.875 |  | 262.375 | 255295 | [7 empty] | 0
Best of breed 3 Total (business intelligence) | [5 empty] | 19 |  |  | 19 | 24700 | [7 empty] | 0
Total Implementation (D) | 9 | 101 | 72 | 214.2406 | 354.9906 | 118.75 | 155.8939 | 50 | 1075.875 | 1048193.3019 | 60 | 120 | 180 | 0 | 120 | 0 | 0 | 480
Travel expenses | 18000
768198.3019
COST PER PROFILE ( € ) excl. tax (for the domain) / incl. Travel expenses | 16200 | 111100 | 61200 | 321360.8491 | 276892.6415 | 154375 | 81064.8113 | 26000
TOTAL COST ( € ) excl. tax for the domain | 1066193.3019
Average daily rate | 974.2705
Note on C56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added by Camille, to be equivalent by Netsuite

## SAP Interface details
|  | Company name | KPMG
|  | Solution name | SAP S/4HANA Public Cloud
INTERFACES DETAILS
Fields to be completed by applicant
ID | No. | Application name (t obe interfaced with the future ERP system | Business objects exchanged | Estimation in number of days
|  | Interfaces with existing solutions |  |  |  | 1500 | 780 | 520
001 | 1 | Trust Pair | Supplier database verification (vendor master data, risk scoring, validation status) | 19 |  | 20.75% | 20.75% | 58.49%
002 | 2 | Agicap | Treasury & cash management (cash positions, bank transactions, forecasts) | 15
003 | 3 | E-invoicing platform (TBD) | E-invoicing management (customer & supplier invoices, statuses, legal archiving references) | 0 |  | 13.4906 | 13.4906 | 38.0189
004 | 4 | ADP | Payroll data, HR master data | 2
005 | 5 | Lucca | People management | 2
006 | 6 | Workday Adaptive Planning | Budget data, forecasts, analytical structures | 15
007 | 7 | Workiva | Financial reporting data (journals, adjustments, disclosure items) | 0
Interfaces with possible future solutions
008 | 8 | 3PL | Inventory, shipment, and logistics data | 27 | per partner
009 | 9 | Order to cash partner | Order-to-cash information, including orders, billing, and customer transactions | 15 | per partner
010 | 10 | Production partner | Production data such as manufacturing orders, consumption, and outputs with the production system. | 23 | per partner

## SAP Cash forecast
|  | Company name | KPMG
|  | Solution name | SAP S/4HANA Public Cloud
DETAIL OF CASH FORECAST
Cash-out forecast for Abivax
Cash-out forecast for Abivax | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Build | 786198.3019 | 279995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1066193.3019
Run (license cost and TMA) | 136745 | 218340 | 218340 | 218340 | 218340 | 218340 | 218340 | 218340 | 218340 | 218340 | 2101805
43958
81595
Comms Camille | 5 year contracts, possible to go up to 7
Subjected to CPI / all years. Starting Y2
Already apply a commercial effort.
Please use assumptions for roll-out detailed in the RFP main document.
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 717670 de base, j’ai modifié car pas aligné
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: E-invoicing + BI
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 92k given during audition for licences

## SAP Financial analysis
L
| Company name | KPMG
| Solution name | SAP S/4HANA Public Cloud
DETAIL OF FINANCIAL ANALYSIS
ERP solution - Integrator
Saas
Overall cost over 3 years |  | 1721213.3019
Overall cost over 5 years |  | 2157893.3019
Overall cost over 10 years |  | 3249593.3019
Build | Project management | 146700
| Initialization | 5800
| Solution design | 114410
| Solution implementation | 246408.3019
| Data recovery | 0
| Acceptance | 84100
| Training | 0
| Production start-up and assistance | 109680
| Maintenance and user support during the warranty phase | 0
| Reversibility management | 0
| Best-of-breed implementation | 341095
| Travel expenses | 18000
| Sub-total “Build” (One-Off) | 1066193.3019
Run | SAAS rent (annual) | 161090
| SaaS rent (annual unit basis) | 348.4381
| SaaS rent (monthly basis) | 13424.1667
| SaaS rent (annual basis) | 115333
| Best of Breed SaaS rent (annual basis) | 45757
| Hosting subscription (annual) | 0
| Other costs | 0
| TMA (annual) | 57250
| Support (annual basis) | 14400
| TMA rent (annual basis) | 42850
Other support / maintenance services
| Sub-total “Run” Saas (annual) | 218340
| Sub-total “Run” Saas (5 years) | 1091700
Total (man days) |  | 1075.875
Integrator's average daily rate |  | 974.2705
Abivax Workload |  | 480

## RUN (hidden)
|  | x | [6 empty] | x | [6 empty] | x | [6 empty] | KPMG | [6 empty] | x | [6 empty] | x
|  | Oracle | [6 empty] | Sage | [6 empty] | IFS Cloud | [6 empty] | Microsoft | [6 empty] | SAP | [6 empty] | Infor
|  |  | License cost | [6 empty] | License cost | [6 empty] | License cost | [6 empty] | License cost | [6 empty] | License cost | [6 empty] | License cost
Criteria | Quantity | Unit price by year by user | Acquisition cost Public price | Applicable rebate | Final offer V1 | Comments | Criteria | Quantity | Unit price by year by user | Acquisition cost Public price | Applicable rebate | Final offer V1 | Comments | Criteria | Quantity | Unit price by year by user | Acquisition cost Public price | Applicable rebate | Final offer V1 | Comments | Criteria | Quantity | Unit price by year by user | Acquisition cost Public price | Applicable rebate | Final offer V1 | Comments | Criteria | Quantity | Unit price by year by user | Acquisition cost Public price | Applicable rebate | Final offer V1 | Comments | Criteria | Quantity | Unit price by year by user | Acquisition cost Public price | Applicable rebate | Final offer V1 | Comments
Licences Core model | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Licences Core model | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Licences Core model | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Licences Core model | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Licences Core model | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Licences Core model | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
Sub-total for licences cost (core model exc. Best of breed) | 0 | 0 | 0 |  | 0 |  | Sub-total for licences cost (core model exc. Best of breed) | 0 | 0 | 0 |  | 0 |  | Sub-total for licences cost (core model exc. Best of breed) | 0 | 0 | 0 |  | 0 |  | Sub-total for licences cost (core model exc. Best of breed) | 0 | 0 | 0 |  | 0 |  | Sub-total for licences cost (core model exc. Best of breed) | 0 | 0 | 0 |  | 0 |  | Sub-total for licences cost (core model exc. Best of breed) | 0 | 0 | 0 |  | 0
Add-ons, best-of-breed and other licenses by domain : | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Add-ons, best-of-breed and other licenses by domain : | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Add-ons, best-of-breed and other licenses by domain : | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Add-ons, best-of-breed and other licenses by domain : | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Add-ons, best-of-breed and other licenses by domain : | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Add-ons, best-of-breed and other licenses by domain : | Nb of users | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
Sub-total for licences cost (Best of breed) | 0 | 0 | 0 |  | 0 |  | Sub-total for licences cost (Best of breed) | 0 | 0 | 0 |  | 0 |  | Sub-total for licences cost (Best of breed) | 0 | 0 | 0 |  | 0 |  | Sub-total for licences cost (Best of breed) | 0 | 0 | 0 |  | 0 |  | Sub-total for licences cost (Best of breed) | 0 | 0 | 0 |  | 0 |  | Sub-total for licences cost (Best of breed) | 0 | 0 | 0 |  | 0
Support / Maintenance | Day | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Support / Maintenance | Day | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Support / Maintenance | Day | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Support / Maintenance | Day | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Support / Maintenance | Day | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax |  | Support / Maintenance | Day | Unit price € Excluding tax | € Excluding tax (by year) | % | € Excluding tax
Support (annual basis) |  |  | 0 |  | 0 |  | Support (annual basis) |  |  | 0 |  | 0 |  | Support (annual basis) |  |  | 0 |  | 0 |  | Support (annual basis) |  |  | 0 |  | 0 |  | Support (annual basis) |  |  | 0 |  | 0 |  | Support (annual basis) |  |  | 0 |  | 0
Maintenance (TMA - annual basis) |  |  | 0 |  | 0 |  | Maintenance (TMA - annual basis) |  |  | 0 |  | 0 |  | Maintenance (TMA - annual basis) |  |  | 0 |  | 0 |  | Maintenance (TMA - annual basis) |  |  | 0 |  | 0 |  | Maintenance (TMA - annual basis) |  |  | 0 |  | 0 |  | Maintenance (TMA - annual basis) |  |  | 0 |  | 0
List other services offered |  |  | 0 |  | 0 |  | List other services offered |  |  | 0 |  | 0 |  | List other services offered |  |  | 0 |  | 0 |  | List other services offered |  |  | 0 |  | 0 |  | List other services offered |  |  | 0 |  | 0 |  | List other services offered |  |  | 0 |  | 0
List other services offered |  |  | 0 |  | 0 |  | List other services offered |  |  | 0 |  | 0 |  | List other services offered |  |  | 0 |  | 0 |  | List other services offered |  |  | 0 |  | 0 |  | List other services offered |  |  | 0 |  | 0 |  | List other services offered |  |  | 0 |  | 0
Total other services offered | 0 | 0 | 0 |  | 0 |  | Total other services offered | 0 | 0 | 0 |  | 0 |  | Total other services offered | 0 | 0 | 0 |  | 0 |  | Total other services offered | 0 | 0 | 0 |  | 0 |  | Total other services offered | 0 | 0 | 0 |  | 0 |  | Total other services offered | 0 | 0 | 0 |  | 0
Other cost items (infrastructure, etc.) | Quantity | Unit price € Excluding tax | € Excluding tax | % | € Excluding tax |  | Other cost items (infrastructure, etc.) | Quantity | Unit price € Excluding tax | € Excluding tax | % | € Excluding tax |  | Other cost items (infrastructure, etc.) | Quantity | Unit price € Excluding tax | € Excluding tax | % | € Excluding tax |  | Other cost items (infrastructure, etc.) | Quantity | Unit price € Excluding tax | € Excluding tax | % | € Excluding tax |  | Other cost items (infrastructure, etc.) | Quantity | Unit price € Excluding tax | € Excluding tax | % | € Excluding tax |  | Other cost items (infrastructure, etc.) | Quantity | Unit price € Excluding tax | € Excluding tax | % | € Excluding tax
Hosting subscription (annual) |  |  | 0 |  | 0 |  | Hosting subscription (annual) |  |  | 0 |  | 0 |  | Hosting subscription (annual) |  |  | 0 |  | 0 |  | Hosting subscription (annual) |  |  | 0 |  | 0 |  | Hosting subscription (annual) |  |  | 0 |  | 0 |  | Hosting subscription (annual) |  |  | 0 |  | 0
List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0
List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0
List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0 |  | List the other cost items (hardware, servers, etc.) from an infrastructure point of view |  |  | 0 |  | 0
Sub-total for other items | 0 | 0 | 0 |  | 0 |  | Sub-total for other items | 0 | 0 | 0 |  | 0 |  | Sub-total for other items | 0 | 0 | 0 |  | 0 |  | Sub-total for other items | 0 | 0 | 0 |  | 0 |  | Sub-total for other items | 0 | 0 | 0 |  | 0 |  | Sub-total for other items | 0 | 0 | 0 |  | 0
| TOTAL |  |  |  | 0 |  |  | TOTAL |  |  |  | 0 |  |  | TOTAL |  |  |  | 0 |  |  | TOTAL |  |  |  | 0 |  |  | TOTAL |  |  |  | 0 |  |  | TOTAL |  |  |  | 0

## BUILD (hidden)
DETAIL of BUILD
Is the project costed on a fixed-price basis? | [19 empty] | Is the project costed on a fixed-price basis? | [19 empty] | Is the project costed on a fixed-price basis? | [19 empty] | Is the project costed on a fixed-price basis? | [19 empty] | Is the project costed on a fixed-price basis? | [19 empty] | Is the project costed on a fixed-price basis?
Fields to be completed by applicant |  | Oracle - x | [17 empty] | Fields to be completed by applicant |  | Sage - x | [17 empty] | Fields to be completed by applicant |  | IFS Cloud - x | [17 empty] | Fields to be completed by applicant |  | Microsoft - x | [17 empty] | Fields to be completed by applicant |  | SAP - x | [17 empty] | Fields to be completed by applicant |  | Infor - x
Phases | Workloads Provider / profile / phase | [9 empty] | GC workloads / profile / phase | [7 empty] | Assumptions / Comments | Phases | Workloads Provider / profile / phase | [9 empty] | GC workloads / profile / phase | [7 empty] | Assumptions / Comments | Phases | Workloads Provider / profile / phase | [9 empty] | GC workloads / profile / phase | [7 empty] | Assumptions / Comments | Phases | Workloads Provider / profile / phase | [9 empty] | GC workloads / profile / phase | [7 empty] | Assumptions / Comments | Phases | Workloads Provider / profile / phase | [9 empty] | GC workloads / profile / phase | [7 empty] | Assumptions / Comments | Phases | Workloads Provider / profile / phase | [9 empty] | GC workloads / profile / phase | [7 empty] | Assumptions / Comments
| Project Director Profile | Project Manager Profile | Technical Consultant Profile | Functional Consultant Profile | Trainer Profile | IT Architect Profile | Profile xxxxxx | Profile xxxxxx | Total (Days) | Total € by phase | Project Manager | BPO | Key User | Users | IT team member (technical responsible) | Profile xxxxxx | Profile xxxxxx | Total (D) | Total € by phase |  | Project Director Profile | Project Manager Profile | Technical Consultant Profile | Functional Consultant Profile | Trainer Profile | IT Architect Profile | Profile xxxxxx | Profile xxxxxx | Total (Days) | Total € by phase | Project Manager | BPO | Key User | Users | IT team member (technical responsible) | Profile xxxxxx | Profile xxxxxx | Total (D) | Total € by phase |  | Project Director Profile | Project Manager Profile | Technical Consultant Profile | Functional Consultant Profile | Trainer Profile | IT Architect Profile | Profile xxxxxx | Profile xxxxxx | Total (Days) | Total € by phase | Project Manager | BPO | Key User | Users | IT team member (technical responsible) | Profile xxxxxx | Profile xxxxxx | Total (D) | Total € by phase |  | Project Director Profile | Project Manager Profile | Technical Consultant Profile | Functional Consultant Profile | Trainer Profile | IT Architect Profile | Profile xxxxxx | Profile xxxxxx | Total (Days) | Total € by phase | Project Manager | BPO | Key User | Users | IT team member (technical responsible) | Profile xxxxxx | Profile xxxxxx | Total (D) | Total € by phase |  | Project Director Profile | Project Manager Profile | Technical Consultant Profile | Functional Consultant Profile | Trainer Profile | IT Architect Profile | Profile xxxxxx | Profile xxxxxx | Total (Days) | Total € by phase | Project Manager | BPO | Key User | Users | IT team member (technical responsible) | Profile xxxxxx | Profile xxxxxx | Total (D) | Total € by phase |  | Project Director Profile | Project Manager Profile | Technical Consultant Profile | Functional Consultant Profile | Trainer Profile | IT Architect Profile | Profile xxxxxx | Profile xxxxxx | Total (Days) | Total € by phase | Project Manager | BPO | Key User | Users | IT team member (technical responsible) | Profile xxxxxx | Profile xxxxxx | Total (D) | Total € by phase
Average daily rate by profile (in € excl. tax) | [19 empty] | Average daily rate by profile (in € excl. tax) | [19 empty] | Average daily rate by profile (in € excl. tax) | [19 empty] | Average daily rate by profile (in € excl. tax) | [19 empty] | Average daily rate by profile (in € excl. tax) | [19 empty] | Average daily rate by profile (in € excl. tax)
| Estimated workload (in days) | [9 empty] | Estimated workload (in days) | [9 empty] | Estimated workload (in days) | [9 empty] | Estimated workload (in days) | [9 empty] | Estimated workload (in days) | [9 empty] | Estimated workload (in days) | [9 empty] | Estimated workload (in days) | [9 empty] | Estimated workload (in days) | [9 empty] | Estimated workload (in days) | [9 empty] | Estimated workload (in days) | [9 empty] | Estimated workload (in days) | [9 empty] | Estimated workload (in days)
Project management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project follow-up | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Project follow-up | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Project follow-up | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Project follow-up | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Project follow-up | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Project follow-up | [8 empty] | 0 | 0 | [7 empty] | 0
Initialization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Initialization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Initialization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Initialization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Initialization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Initialization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project scoping and launch | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Project scoping and launch | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Project scoping and launch | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Project scoping and launch | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Project scoping and launch | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Project scoping and launch | [8 empty] | 0 | 0 | [7 empty] | 0
Technical analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Technical analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Technical analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Technical analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Technical analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Technical analysis | [8 empty] | 0 | 0 | [7 empty] | 0
Functional analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Functional analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Functional analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Functional analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Functional analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Functional analysis | [8 empty] | 0 | 0 | [7 empty] | 0
Data analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Data analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Data analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Data analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Data analysis | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Data analysis | [8 empty] | 0 | 0 | [7 empty] | 0
Preparation of environments | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Preparation of environments | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Preparation of environments | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Preparation of environments | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Preparation of environments | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Preparation of environments | [8 empty] | 0 | 0 | [7 empty] | 0
Solution design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Solution design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Solution design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Solution design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Solution design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Solution design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drafting of solution design file | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Drafting of solution design file | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Drafting of solution design file | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Drafting of solution design file | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Drafting of solution design file | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Drafting of solution design file | [8 empty] | 0 | 0 | [7 empty] | 0
Definition of development plan | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Definition of development plan | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Definition of development plan | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Definition of development plan | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Definition of development plan | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Definition of development plan | [8 empty] | 0 | 0 | [7 empty] | 0
Initialization and design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Initialization and design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Initialization and design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Initialization and design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Initialization and design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Initialization and design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solution implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Solution implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Solution implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Solution implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Solution implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Solution implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Specific development and parameterization | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Specific development and parameterization | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Specific development and parameterization | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Specific development and parameterization | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Specific development and parameterization | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Specific development and parameterization | [8 empty] | 0 | 0 | [7 empty] | 0
Realization of interfaces | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Realization of interfaces | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Realization of interfaces | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Realization of interfaces | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Realization of interfaces | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Realization of interfaces | [8 empty] | 0 | 0 | [7 empty] | 0
Production of editions | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production of editions | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production of editions | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production of editions | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production of editions | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production of editions | [8 empty] | 0 | 0 | [7 empty] | 0
Production of indicators and dashboards | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production of indicators and dashboards | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production of indicators and dashboards | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production of indicators and dashboards | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production of indicators and dashboards | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production of indicators and dashboards | [8 empty] | 0 | 0 | [7 empty] | 0
Unit testing | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Unit testing | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Unit testing | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Unit testing | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Unit testing | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Unit testing | [8 empty] | 0 | 0 | [7 empty] | 0
End-to-end testing support | [8 empty] | 0 | 0 | [7 empty] | 0 |  | End-to-end testing support | [8 empty] | 0 | 0 | [7 empty] | 0 |  | End-to-end testing support | [8 empty] | 0 | 0 | [7 empty] | 0 |  | End-to-end testing support | [8 empty] | 0 | 0 | [7 empty] | 0 |  | End-to-end testing support | [8 empty] | 0 | 0 | [7 empty] | 0 |  | End-to-end testing support | [8 empty] | 0 | 0 | [7 empty] | 0
Data migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Data migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Data migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Data migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Data migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Data migration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cleaning and standardization of repositories | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Cleaning and standardization of repositories | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Cleaning and standardization of repositories | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Cleaning and standardization of repositories | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Cleaning and standardization of repositories | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Cleaning and standardization of repositories | [8 empty] | 0 | 0 | [7 empty] | 0
Formalization of target data architecture | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Formalization of target data architecture | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Formalization of target data architecture | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Formalization of target data architecture | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Formalization of target data architecture | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Formalization of target data architecture | [8 empty] | 0 | 0 | [7 empty] | 0
Data migration | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Data migration | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Data migration | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Data migration | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Data migration | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Data migration | [8 empty] | 0 | 0 | [7 empty] | 0
Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Support during acceptance phase | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Support during acceptance phase | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Support during acceptance phase | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Support during acceptance phase | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Support during acceptance phase | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Support during acceptance phase | [8 empty] | 0 | 0 | [7 empty] | 0
Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formalization of training plan and training materials (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Formalization of training plan and training materials (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Formalization of training plan and training materials (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Formalization of training plan and training materials (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Formalization of training plan and training materials (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Formalization of training plan and training materials (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0
Conduct training sessions (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Conduct training sessions (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Conduct training sessions (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Conduct training sessions (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Conduct training sessions (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Conduct training sessions (for users, tool admins and managers) | [8 empty] | 0 | 0 | [7 empty] | 0
Production start-up and assistance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Production start-up and assistance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Production start-up and assistance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Production start-up and assistance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Production start-up and assistance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Production start-up and assistance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decommissioning and changeover | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Decommissioning and changeover | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Decommissioning and changeover | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Decommissioning and changeover | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Decommissioning and changeover | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Decommissioning and changeover | [8 empty] | 0 | 0 | [7 empty] | 0
Production start-up and assistance | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production start-up and assistance | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production start-up and assistance | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production start-up and assistance | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production start-up and assistance | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Production start-up and assistance | [8 empty] | 0 | 0 | [7 empty] | 0
Maintenance and user support during the warranty phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maintenance and user support during the warranty phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maintenance and user support during the warranty phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maintenance and user support during the warranty phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maintenance and user support during the warranty phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maintenance and user support during the warranty phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maintenance and user support | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Maintenance and user support | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Maintenance and user support | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Maintenance and user support | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Maintenance and user support | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Maintenance and user support | [8 empty] | 0 | 0 | [7 empty] | 0
Reversibility management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reversibility management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reversibility management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reversibility management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reversibility management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reversibility management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reversibility management | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Reversibility management | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Reversibility management | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Reversibility management | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Reversibility management | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Reversibility management | [8 empty] | 0 | 0 | [7 empty] | 0
Best of breed implementation (only total amounts for each best of breed solution - you can copy this tab to make a separate financial grid for each solution) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Best of breed implementation (only total amounts for each best of breed solution - you can copy this tab to make a separate financial grid for each solution) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Best of breed implementation (only total amounts for each best of breed solution - you can copy this tab to make a separate financial grid for each solution) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Best of breed implementation (only total amounts for each best of breed solution - you can copy this tab to make a separate financial grid for each solution) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Best of breed implementation (only total amounts for each best of breed solution - you can copy this tab to make a separate financial grid for each solution) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Best of breed implementation (only total amounts for each best of breed solution - you can copy this tab to make a separate financial grid for each solution) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Best of breed 1 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 1 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 1 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 1 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 1 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 1 Total | [8 empty] | 0 | 0 | [7 empty] | 0
Best of breed 2 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 2 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 2 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 2 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 2 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 2 Total | [8 empty] | 0 | 0 | [7 empty] | 0
Best of breed 3 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 3 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 3 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 3 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 3 Total | [8 empty] | 0 | 0 | [7 empty] | 0 |  | Best of breed 3 Total | [8 empty] | 0 | 0 | [7 empty] | 0
Total Implementation (D) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total Implementation (D) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total Implementation (D) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total Implementation (D) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total Implementation (D) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total Implementation (D) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel expenses | [19 empty] | Travel expenses | [19 empty] | Travel expenses | [19 empty] | Travel expenses | [19 empty] | Travel expenses | [19 empty] | Travel expenses
COST PER PROFILE ( € ) excl. tax (for the domain) / incl. Travel expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | COST PER PROFILE ( € ) excl. tax (for the domain) / incl. Travel expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | COST PER PROFILE ( € ) excl. tax (for the domain) / incl. Travel expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | COST PER PROFILE ( € ) excl. tax (for the domain) / incl. Travel expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | COST PER PROFILE ( € ) excl. tax (for the domain) / incl. Travel expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | COST PER PROFILE ( € ) excl. tax (for the domain) / incl. Travel expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL COST ( € ) excl. tax for the domain | 0 | [18 empty] | TOTAL COST ( € ) excl. tax for the domain | 0 | [18 empty] | TOTAL COST ( € ) excl. tax for the domain | 0 | [18 empty] | TOTAL COST ( € ) excl. tax for the domain | 0 | [18 empty] | TOTAL COST ( € ) excl. tax for the domain | 0 | [18 empty] | TOTAL COST ( € ) excl. tax for the domain | 0
Average daily rate | 0 | [18 empty] | Average daily rate | 0 | [18 empty] | Average daily rate | 0 | [18 empty] | Average daily rate | 0 | [18 empty] | Average daily rate | 0 | [18 empty] | Average daily rate | 0