## CFGI Valuations
|  | Fair value | Sensitivy analysis | Suggested assumptions / data for sensitivity analyses
| Heights notes | X | N/A | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving either scenario (+10% / -10%)
| Kreos/Claret debt component | N/A | N/A | credit spread +100bp
| K/C Tr B MRI | X | N/A
2024-09-30 | K/C Tr C MRI | X | N/A
| K/C Tranche A-B warrants | X | N/A | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving either scenario (+10% / -10%)
| K/C Tranche C warrants | X | N/A | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving either scenario (+10% / -10%)
| Heights notes | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving the HTM scenario (+10 / -10%)
| Kreos/Claret debt component | X | X | credit spread +100bp
| K/C Tr B MRI | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving the Final Redemption scenario (+5 / -5%), discount rate (+1% point) | new
| K/C Tr C MRI | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving the Final Redemption scenario (+5 / -5%), discount rate (+1% point) | new
2024-12-31 | K/C Tranche A-B warrants | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving either scenario (+5 / -5%)
| K/C Tranche C warrants | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving either scenario (+5 / -5%)
| K/C debt components (A/B/C) updated amortised costs schedules with the new interest rates (changes from September to December) | X | N/A | N/A | new
| Heights notes | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving the HTM scenario (+10 / -10%)
| Kreos/Claret debt component | X | X | credit spread +100bp
| K/C Tr B MRI | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving the Final Redemption scenario (+5 / -5%), discount rate (+1% point)
| K/C Tr C MRI | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving the Final Redemption scenario (+5 / -5%), discount rate (+1% point)
2025-06-30 | K/C Tranche A-B warrants | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving either scenario (+5 / -5%)
| K/C Tranche C warrants | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving either scenario (+5 / -5%)
|  | Fair value | Sensitivy analysis | Suggested assumptions / data for sensitivity analyses
| K/C Tr B MRI | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving the Final Redemption scenario (+5 / -5%), discount rate (+1% point)
2025-09-30 | K/C Tr C MRI | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving the Final Redemption scenario (+5 / -5%), discount rate (+1% point)
| Kreos/Claret debt component | X | X | credit spread +100bp
| K/C Tr B MRI | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving the Final Redemption scenario (+5 / -5%), discount rate (+1% point)
2025-12-31 | K/C Tr C MRI | X | X | share price (+1€), volatility (+1% point), risk-free rate (+100bp), probability of achieving the Final Redemption scenario (+5 / -5%), discount rate (+1% point)
| Kreos/Claret debt component | X | X | credit spread +100bp
obtained
to be obtained
NB : only required if the sensitivy analysis remains relevant (if the FV is locked at 0 due to the gain made on the conversion of the warrants and OCABSA, the analysis is not required). In this case, please provide a wording explaining the rationale

## Timeline Q1 2026
May 1, 8 and 14 are public holidays in France
[15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
|  |  | October |  |  |  | November |  |  |  | December |  |  |  | 2: January; 6: February; 12: March; 15: April; 19: May; 23: June; 28: July; 32: August; 36: September; 41: October; 45: November; 49: December; 2: January; 6: February; 10: March; 15: April; May 1, 8 and 14 are public holidays in France 19: May; May 1, 8 and 14 are public holidays in France 23: June; May 1, 8 and 14 are public holidays in France 28: July; May 1, 8 and 14 are public holidays in France 32: August; May 1, 8 and 14 are public holidays in France 37: September
|  | Week commencing | 7 | 14 | 21 | 28 | 4 | 11 | 28 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 4 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28
Q2 2025 | bar: October 7 to May 26; June 16 to August 25; September 8 to September 29
To be confirmed by Abivax |  | Abx / InExtenso - Cut-off deadline | July 7: 7
To be confirmed by Abivax |  | Abx / InExtenso - Internal accounts review | bar: July 7
To be confirmed by Abivax |  | Abx / Certent: IFRS 2 results | July 14: 15
To be confirmed by Abivax |  | Abx / InExtenso - Balance French & U.S. | July 14: 15
To confirm with CFGI |  | CFGI - H1 25 valuation works | July 7: 7
|  | KPMG - IAS19 Report | July 7: 11
|  | KPMG - Royalty certificates fair value | July 7: 9; July 14: Assuming no BP update
|  | KPMG - Financial instruments valuation works | July 7: 9
|  | KPMG - IFRS FS (Excel balance & tables) | July 14: 15
|  | KPMG - IFRS FS (Word notes to the FS) | July 28: 30
KPMG - French document rollforward in Workiva | bar: June 2
Abx - 6-K document rollforward in Workiva | bar: June 2
Abx "MD&A" draft and PY figures | bar: June 2; July 14 to July 21
KPMG - "MD&A" (input of HY25 figures & review) | bar: July 28
|  | KPMG - Translation from 6-K | August 4: 2025-08-04
|  | Abx - Preparation of the RFS | August 4: 04/08=>05/08
To be confirmed with Workiva |  | Workiva - 6-K Tagging | August 4: 30/07=>7/08; August 18: Tagging requirement to be confirmed
To be confirmed by PwC |  | PwC - Limited review HY 2025 French GAAP + Abx LLC | July 21: x; August 18: closing meeting on July 23th (French GAAP / LLC)
To be confirmed by PwC |  | PwC - Limited review HY 2025 IFRS | bar: July 28 to August 4
To be confirmed by PwC |  | PwC - Review of 6-K | bar: August 4
To be confirmed by PwC |  | PwC - Review of HY Financial report | August 4: 06/08=>08/08
|  | Audit Committee | August 4: 6
|  | Board Meeting | August 4: 6
|  | 6-K filing | August 11: 11
|  | HY Financial report filing | August 11: 11
Q3 2025 | bar: October 7 to May 26; June 16 to August 25; September 8 to September 29
To be confirmed by Abivax |  | Abx / InExtenso - Cut-off deadline | October 6: 8
To be confirmed by Abivax |  | Abx / InExtenso - Internal accounts review | bar: October 6
To be confirmed by Abivax |  | Abx / Certent: IFRS 2 results | October 13: 15
To be confirmed by Abivax |  | Abx / InExtenso - Balance French & U.S. | October 13: 17
To confirm with CFGI |  | CFGI - Q3 25 valuation works | October 6: 7
|  | KPMG - IAS19 Report | October 6: 13
|  | KPMG - Royalty certificates fair value | October 6: 9; October 13: Assuming no BP update => Confirmed, no BP update
|  | KPMG - Financial instruments valuation works | October 6: 9
KPMG - IFRS FS (Excel balance & tables) | bar: September 29; October 20 to October 27
KPMG - IFRS FS (Word notes to the FS) | bar: October 27 to November 3
KPMG - French document rollforward in Workiva | bar: September 1
Abx - 6-K document rollforward in Workiva | bar: September 1
Abx "MD&A" draft and PY figures | bar: September 1; October 20 to October 27
KPMG - "MD&A" (input of Q325 figures & review) | bar: November 3
KPMG - Translation from 6-K | bar: October 6; November 3 to November 10
Abx - Preparation of the RFS | bar: November 3 to November 17
To be confirmed with Workiva |  | Workiva - 6-K Tagging | bar: November 3 to November 17
To be confirmed by PwC | To be completed by PwC | PwC - Limited review HY 2025 French GAAP + Abx LLC | November 24: closing meeting on November 3 (French GAAP / LLC)
To be confirmed by PwC | To be completed by PwC | PwC - Limited review Q3 2025 IFRS | bar: November 10 to November 24
To be confirmed by PwC | To be completed by PwC | PwC - Review of 6-K | bar: November 3 to November 24
To be confirmed by PwC | To be completed by PwC | PwC - Review of Q3 Financial report | bar: November 17 to November 24
|  | Audit Committee | December 8: 11
|  | Board Meeting | December 8: 11
|  | 6-K filing | December 15: 15
|  | Q3 Financial report filing | December 15: 15
FY 2025 | bar: October 7 to May 26; June 16 to August 25; September 8 to September 29
To be confirmed by Abivax | To be completed by Abivax | Abx / InExtenso - Cut-off deadline | January 4: 8
To be confirmed by Abivax | To be completed by Abivax | Abx / InExtenso - Internal accounts review | bar: January 4
To be confirmed by Abivax | To be completed by Abivax | Abx / Certent: IFRS 2 results | January 12: 16
To be confirmed by Abivax | To be completed by Abivax | Abx / InExtenso - Balance French & U.S. | January 12: 16
To confirm with CFGI |  | CFGI - FY 25 valuation works | January 4: 8
|  | KPMG - IAS19 Report | January 4: 12
|  | KPMG - Royalty certificates fair value | January 4: 12; January 12: Assuming no BP update
|  | KPMG - Financial instruments valuation works | January 4: 12
|  | KPMG - IFRS FS (Excel balance & tables) | November 3: to be discussed
KPMG - IFRS FS (Word notes to the FS) | bar: January 26 to February 2
|  | KPMG - French document rollforward in Workiva | November 3: to be discussed
|  | Abx - 20F document rollforward in Workiva | November 3: to be discussed
|  | Abx "MD&A" draft and PY figures | November 3: to be discussed
KPMG - "MD&A" (input of FY25 figures & review) | bar: February 2
KPMG - Translation from 20F | bar: December 29; February 2 to February 9
Abx - Preparation of the URD | bar: December 29; February 2 to February 16
To be confirmed with Workiva |  | Workiva - 6-K Tagging | bar: February 2 to February 16
To be confirmed by PwC | To be completed by PwC | PwC - Audit of FY2025 French GAAP + Abx LLC | February 23: closing meeting on Feb 2nd (French GAAP / LLC)
To be confirmed by PwC | To be completed by PwC | PwC - Limited review FY 2025 IFRS | bar: February 9 to February 23
To be confirmed by PwC | To be completed by PwC | PwC - Review of 20-F | bar: February 2 to February 23
To be confirmed by PwC | To be completed by PwC | PwC - Review of URD | bar: February 16 to March 2
| To be completed by PwC | PwC - Review of URD tagging | bar: February 23 to March 2
| To be completed by Abivax | Audit Committee | February 16: To be confirmed; March 16: 19
| To be completed by Abivax | Board Meeting | March 16: 19
| To be completed by Abivax | 20-F filing | March 23: 23
| To be completed by Abivax | URD filing | March 23: 23
| To be completed by Abivax | General Meeting
Q1 2026 | bar: October 7 to May 26; June 16 to August 25; September 8 to September 29
To be confirmed by Abivax |  | Abx / Certent: IFRS 2 results | April 13: 17
To be confirmed by Abivax |  | Abx / InExtenso - Balance French & U.S. | April 13: 17
|  | KPMG - IAS19 Report | April 13: 17
|  | KPMG - Royalty certificates fair value | April 13: 13; April 20: Assuming no BP update
|  | KPMG - Financial instruments valuation works | April 6: 10
|  | KPMG - IFRS FS (Excel balance & tables) | April 27: Excel file ready on April 30 EOD
|  | KPMG - IFRS FS (Word notes to the FS) | May 4: Excel file ready on May 7 EOD
KPMG - French document rollforward in Workiva | bar: March 2
KPMG France - Income tax review (TBD) | bar: May 4 to May 11
KPMG US - Income tax calculation (TBD) | bar: May 4 to May 11
Abx - 6-K document rollforward in Workiva | bar: March 2
Abx "MD&A" draft and PY figures | bar: March 23; April 20 to April 27
KPMG - Item 5 "MD&A" (input of Q126 figures & review) | bar: May 4
|  | KPMG - Translation from 6-K | May 11: 13th morning
|  | Abx - Preparation of the RFT | May 11: 15
To be confirmed with Workiva |  | Workiva - 6-K Tagging | bar: May 11 to May 18
To be confirmed by PwC | To be confirmed by PwC | PwC - Review of Q12026 French GAAP + Abx LLC | May 4: closing meeting on May 8 (French GAAP / LLC)
To be confirmed by PwC | To be confirmed by PwC | PwC - Limited review Q1 2026 IFRS | bar: May 4 to May 11
To be confirmed by PwC | To be confirmed by PwC | PwC - Review of 6-K | bar: May 11 to May 18
To be confirmed by PwC | To be confirmed by PwC | PwC - Review of RFT | May 18: 15th-21st
| To be completed by Abivax | Audit Committee | May 11: To be confirmed
| To be completed by Abivax | Board Meeting | May 18: TBC
| To be completed by Abivax | 6-K filing | May 18: 21
| To be completed by Abivax | Q1 Financial report filing | May 18: 21
Q2 2026 | bar: October 7 to May 26; June 16 to August 25; September 8 to September 29
| To be completed by Abivax | Abx / Certent: IFRS 2 results | July 13: 17
| To be completed by Abivax | Abx / InExtenso - Balance French & U.S. | July 13: 17
KPMG - IAS19 Report | bar: July 13
|  | KPMG - Royalty certificates fair value | July 13: Assuming no BP update
KPMG - Financial instruments valuation works | bar: July 6
|  | KPMG - IFRS FS (Excel balance & tables) | July 27: Excel file ready on the 31st EOD
|  | KPMG - IFRS FS (Word notes to the FS) | August 3: Notes available on the 7th EOD
KPMG - French document rollforward in Workiva | bar: June 15
KPMG France - Income tax review (TBD) | bar: August 3
KPMG US - Income tax calculation (TBD) | bar: August 3
Abx - 6-K document rollforward in Workiva | bar: June 15
Abx "MD&A" draft and PY figures | bar: June 15; July 20 to July 27
KPMG - Item 5 "MD&A" (input of Q226 figures & review) | bar: August 3
KPMG - Translation from 6-K | bar: June 29; August 3 to August 10
Abx - Preparation of the RFS | bar: June 29; August 3 to August 17
Workiva - 6-K Tagging | bar: August 3 to August 17
| To be completed by PwC | PwC - Audit of FY2025 French GAAP + Abx LLC | August 24: closing meeting on XXX (French GAAP / LLC)
| To be completed by PwC | PwC - Limited review FY 2025 IFRS | bar: August 10 to August 24
| To be completed by PwC | PwC - Review of 6-K | bar: August 3 to August 24
| To be completed by PwC | PwC - Review of RFS | bar: August 17 to August 31
| To be completed by Abivax | Audit Committee | August 17: To be confirmed
| To be completed by Abivax | Board Meeting | bar: September 14
| To be completed by Abivax | 6-K filing | bar: September 21
| To be completed by Abivax | Q2 Financial report filing | bar: September 21
Note on AS11: Trinidad Mesa: In the morning if not on the 11th end of day

## Q1 2026 closing & PBC
Closing timeline / PBC List ABIVAX Local GAAP & IFRS |  |  | to complete by Abivax
2026-03-31 | En gras : Codification ancienne RCM/ In Bold : Codification former RCM
En Rouge : Non mentionné dans la nouvelle RCM et à rajouter / In Red : Not mentioned in the new RCM and to be added
Préparation du contrôle fini
Item | Nom contrôle Sox | Control ID | (Q1 2026: applicable?) | Status | Target | Owner | Comments | revue du contrôle
French GAAP - Abx SA
Provision for contingencies and charges | Non détaillé dans la RCM : Key car contient la provision relatif au certificat de Royalties (proche de 70 M€ au 30-09-25 | FR-FSCP-41 | X |  | 2026-04-16 | PG | Circularisation à faire
Provision for Forex | Gains an losses calculation and review | FR-FSCP-13E1 | X |  | 2026-04-16 | DJ | Possibilité avant
New fixed assets (new building : invoice and deposit) | Fixed Assets: Mvt Table vs TB reconciliation | FR-FA-C01 |  |  | 2026-03-23 | PG
Fixed assets: identification of invoices | Fixed Assets: Mvt Table vs TB reconciliation | FR-FA-C01 | X |  | 2026-03-23 | PG
Fixed assets : réceipt from IE FA follow up | Fixed Assets: Mvt Table vs TB reconciliation | FR-FA-C01 | X |  | 2026-04-02 | In Extenso/PG
Fixed assets: entries depreciation | Fixed Assets: Mvt Table vs TB reconciliation | FR-FA-C01 | X |  | 2026-04-02 | In Extenso
Fixed assets: table of change in PP&E & intangibles | Fixed Assets: Mvt Table vs TB reconciliation | FR-FA-C01 | X |  | 2026-04-02 | PG
Fixed assets: intangibles | Revue des Immos Incorporelles | FR-FA-C02 | X |  | 2026-04-02 | PG
Financial fixed assets | Revue des Immos Financières | FR-FA-C09 | X |  | 2026-04-02 | PG |  |  | J'ai rajouté cette ligne car le contrôle est fait et formalisé et indépendant des autres immobilisations
Liquidity contract |  |  | N/A |  | N/A
Review 471 (compte d'attente) |  |  | X |  | 2026-04-07 | PG | A regarder régulièrement
Payroll entries | Payroll Expense Journal Entry | FR-HTR-12 | X |  | 2026-03-26 | ADP/ PG | Comptabilisation de l'OD de paie
Rapprochement compta//Journal de paie | Payroll BS Reconciliation | FR-HTR-15_1 | X |  | 2026-04-07 | PG
Rapprochement compa//DSN//Journal de paie | Payroll BS Reconciliation (non identifié dans RCM : Non Key ?) | FR-HTR-15_3 | X |  | 2026-04-07 | PG | Dépendant de la mise à disposition des DSN par ADP
Revus des dettes sociales | Payroll BS Reconciliation | FR-HTR-15_2 | X |  | 2026-04-07 | PG
Welcome Bonus spread | (non identifié dans RCM : Non Key | FR-HTR-19 | X | Done | 2026-03-16 | PG
Accrual for paid leave | Vacation accrual | FR-HTR-14 | X |  | 2026-03-31 | ADP/ PG | Dépendant de la mise à disposition du document par ADP
Accrual social charges on free shares | Accrual for social charges on free shares (fait parti du contrôle global PRC | FR-FSCP-41 | X |  | 2026-04-10 | Trinidad/PG
Bonus' accruals | Bonus Accrual | FR-HTR-13 | X |  | 2026-04-08 | Trinidad/PG
Directors' Fees | (non identifié dans RCM : Key ? | FR-HTR-20 | X |  | 2026-03-29 | Trinidad/PG
HR traffic ( Exit and Plan) |  |  | X |  | 2026-04-07 | Trinidad/PG
Bank reconciliation EUR | Bank Reconciliation Review | FR-TR-09 | X |  | 2026-04-02 | JC
Bank reconciliation USD and Account Réévaluation | Bank Reconciliation Review | FR-TR-09 | X |  | 2026-04-02 | DJ
Reconciliation of NCA accounts and CAT and reevaluation of USD account | Short Term investment reconciliation (non identifié dans RCM) | FR-TR-12 | X |  | 2026-04-09 | DJ | Attente info RS sur la valo des CODEIS prévu le 09/01/26
End of invoice entries |  |  | X |  | 2026-04-07 | JC
Lettering AP |  |  | X |  | 2026-04-02 | All
dernière Campagne de règlement avant clôture |  |  |  |  | 2026-03-25 | JC/FH
Revue balance agés | Supplier aging review | FR-PTP-17 |  |  | 2026-04-13 | PG | Les contrôles ont été fusionnés
Reconciliation compte général fournisseur vs Compta auxiliaire | Account payable balance sheet reconciliation | FR-PTP-17 |  |  | 2026-04-13 | PG | Les contrôles ont été fusionnés
Rent Hausmann (spread) | (non identifié dans RCM : Non Key |  | X | Done | 2026-03-09 | PG
Advance (CRO) LT | (non identifié dans RCM : Key Reconciliation Advance LT | FR-PTP-27 | X |  | 2026-04-08 | PG / Denis | A revoir uniquement après la MAJ par Fred des coûts par projets
Advance CT | (non identifié dans RCM : Non Key) Reconciliation Advance CT | FR-PTP-26 |  |  | 2026-04-08 | PG / Denis
Prepaid preparation | Prepaid Expense Reconciliation | FR-FSCP-11 | X |  | 2026-04-08 | JC
Prepaid entries | Prepaid Expense Reconciliation | FR-FSCP-11 | X |  | 2026-04-13 | JC
Circularisation interne |  |  | X |  | 2026-03-06 | FP&A and PG
A/P: Accruals calculation (cut-off) R et D | Accruals (la CLI est soit disant couverte par le CTA-06 et la CMC par la CMC-02) | FR-FSCP-12 | X |  | 2026-04-09 | FP&A
A/P: Accruals calculation (cut-off) Marketing | Accruals | FR-FSCP-12 | X |  | 2026-04-09 | Matt | None
A/P: Accruals calculation (cut-off) ADMIN | Accruals | FR-FSCP-12 | X |  | 2026-04-09 | PG
A/P: Accrual entries | Accruals | FR-FSCP-12 | X |  | 2026-04-15 | JC | Ensure that all budget owners are circulated
Reevaluation of Forex for AP | Gains an losses calculation and review | FR-FSCP-13E2 | X |  | 2026-04-10 | DJ
CIR: Obtain Time sheet | Waiting RCM on Tax | FR-TAX-CIR | X |  | 2026-04-07 | TM | Faire demande à E. Leveau (absente jusqu'au 6/10/2025)
CIR: calculation & entries | Research Tax Credit calculation | FR-TAX-CIR | X |  | 16/04/206 | DJ/TM
Contribution AGEPIPH et autres taxes | Non Key / Review Other Tax | FR-TAX-16NK | X |  | 2026-04-08 | PG | certaines taxes serront calculées avec la paie
Tax result calculation | Income Tax calculation | FR-TAX-03NK | X |  | 2026-04-20 | PG | including accumulated tax losses
Checker la cohérence TVA Deductible vs Dette fournisseur |  |  |  |  | 2026-04-13 | PG/DJ
VAT CALCULATION | Vat Calculation | FR-TAX-C01 | X |  | 2026-04-13 | JC/DJ | Possibilité avant
VAT journal entry | Vat Recording | FR-TAX-C02 |  |  | 2026-04-13 | JC/DJ
Financial instruments: obtain information on new Debt if any (legal documents, payment schedule and transaction costs) |  |  | N/A |  | N/A | TM/DJ
Financial instruments: entries |  |  | N/A |  | N/A | DJ
Financial instruments: recap of Kreos/Claret & Heights French GAAP entries (bridge) | Loan Amortization and Interest Review | FR-TR-06G | X |  | N/A | DJ | Revoir les informations
Financial instruments: table of change in financial instruments | Loan Amortization and Interest Review | FR-TR-06G | X |  | NA | In Extenso/DJ | Lié au contrat de liquidité
Interest PGE |  |  | X |  | N/A | DJ | soldé plus d'IC
Accrued Interest on investement (NAC and CAT or DAT if any) | Short Term investment reconciliation (non identifié dans RCM) | FR-TR-12 | X |  | N/A | DJ | Pour les CAT, on peut anticiper
Royalty certificates: Business Plan |  |  | Confirmed: no update |  |  | FP&A | BP provided to KPMG beginning of December 2025
Royalty certificates: Fair value | Non détaillé dans la RCM : Key car contient la provision relatif au certificat de Royalties (proche de 70 M€ au 30-09 | FR-FSCP-41RC | X |  | 2026-04-16 | KPMG
Royalty certificates: Entry | Non détaillé dans la RCM : Key car contient la provision relatif au certificat de Royalties (proche de 70 M€ au 30-09 | FR-FSCP-41RC | X |  | 2026-04-16 | PG
Calculation of Abivax LLC recharge to Abivax SA | Intercompany accounts reconciliation | FR-FSCP-16NK | X |  | 2026-04-16 | DJ / Trinidad
Accrued Interest calculation on LLC current account | Intercompany accounts reconciliation | FR-FSCP-16NK | X |  | 2026-04-16 | DJ
IC reconciliation | Intercompany accounts reconciliation | FR-FSCP-16NK | X |  | 2026-04-16 | DJ
IC current account revaluation | Gains an losses calculation and review | FR-FSCP-13E3 | X |  | 2026-04-16 | DJ | Devrait faire parti du même contrôle que FR-FSCP-16NK sinon le cadrage ne peut pas être effectué
Autres produits (ADS Citibank) |  |  | X |  | 2026-04-15 | PG | Circulariser Citibank via Hema |  | J'ai rajouté cette ligne car le contrôle est fait (pour inclure la circularisation de Hema dans le planning)
Off balancesheet commitment |  |  | X |  | 2026-04-15 | PG/KPMG | Engagé and PIDR/IAS19 (For PIDR : HR to send payroll information to KPMG)
Table of change in equity (Tableau de variation KP) | Review table of change in equity (include FR-EQ-13) | FR-EQ-15 | X |  | 2026-04-16 | PG/Trinidad
Table Capitalisation | Review of Table de Capitalisation | FR-EQ-12 | X |  | 2026-04-16
Trial Balance |  |  | X |  | 2026-04-17 | PG/TM | End of day, 20th morning at the latest |  | ok sent to KPMG on the 20th ( including LLC)
General ledger |  |  | X |  | 2026-04-17 | PG/TM | End of day, 20th morning at the latest
Close Period |  |  | X |  | 2026-04-21 | DJ | Not in the system - the closing in the system once social reviewed by auditors
Plaquette | [5 empty] | PG/TM | To be discuss with MLM
Extourne OD Q1 2026 |  |  | X |  | 2026-04-30 | In Extenso/PG/TM
Local GAAP - Abx LLC
Payroll entries |  |  | X |  | 2026-04-02 | MATT
Bonus accrual |  |  | X |  | 2026-04-02 | MATT
Social charges on Bonus accrual |  |  | X |  | 2026-04-02 | MATT
Welcome Bonus spread |  |  | X |  | 2026-04-02 | MATT
Bank reconciliation USD |  |  | X |  | 2026-04-07 | MATT
Lettering AP and bank |  |  | X |  | 2026-04-07 | MATT
A/P: Accruals calculation (cut-off) MKT & ADMIN |  |  | X |  | 2026-04-09 | MATT
A/P: Accrual entries |  |  | X |  | 2026-04-15 | MATT
Local GAAP TB and General Ledger Abx LLC (without IC recharge) |  |  | X |  | 2026-04-16 | MATT
Abivax LLC recharge to Abivax SA entries |  |  | X |  | 2026-04-16 | MATT / DJ
Fixed assets: identification of invoices |  |  | X |  | 2026-04-08 | MATT
Fixed assets: entries |  |  | X |  | 2026-04-08 | MATT
Fixed assets: table of change in PP&E |  |  | X |  | 2026-04-08 | MATT
Local GAAP TB and General Ledger Abx LLC (with identification of I/C balances) |  |  | X |  | 2026-04-17 | MATT | End of day, 20th morning at the latest
Close Period |  |  | X |  | 2026-04-21 | DJ ? (or MATT) | At the same time as SA
Tax result calculation |  |  | ? |  | 2026-04-20
IFRS (confirmed by KPMG)
P&L By function FR GAAP (Financials light Abivax SA & LLC) |  |  | X |  | 2026-04-21 | FG
Additional short-term investment contracts |  |  | X |  | ASAP | RS
Cash position as of 31/03/26 |  |  | X |  | 10/04/206 | RS
CFGI analyses of any new financing if applicable |  |  | N/A |  | N/A
Amortized cost schedule (Tr B and Tr C if applicable) |  |  | N/A it's repaid |  | N/A | HK
CFGI: debts exctinction memo & related accounting entries in IFRS (Claret OCABSA & K/C Tranches 2 and 3) |  |  | X |  | N/A | CFGI / HK | Il n'y a plus de dettes
CFGI new debts valuations as of 31/03/26 - FV of K/C debt components |  |  | N/A it's repaid |  | N/A | CFGI / HK
EPS: Purchases/sale of Treasury shares report |  |  | N/A |  |  | TM | N/A
IFRS 2/EPS: Cap table including the BCE/BSA/AGA movements |  |  | X |  | 2026-04-10 | TM
IFRS 2 : Updates on departures |  |  | X |  | 2026-04-10 | TM
IFRS 2 : New share-based payments plans if applicable |  |  | X |  | ASAP | TM
IFRS 2 : Results from Certent's calculation tool |  |  | X |  | 2026-04-17 | ME
IFRS 2 : Social charges accrual details with short term / long term split |  |  | X |  | 2026-04-20 | PG/TM
IAS 19 : required data for the valuation report |  |  | X |  | 2026-04-09 | SL | Request sent by KPMG to SL / IH
IFRS 16: Amendment to the LLC Boston HQ contract or Confirmation of the term renewal |  |  | X |  | 2026-04-04 | HK
IFRS 16 : New CNRS lease / amendment to extend the term |  |  | X |  | 2026-04-08 | TM
IFRS 16 : any new other leases of lease modifications if applicable |  |  | X |  | 2026-04-08 | PG
Royalty certificates : sensitivity analyses |  |  | X |  | 2026-04-16 | KPMG
CRO advances : update on the recap file (new advances, progress% (recorded expenses / total budgeted contract expenses)) as of the closing date |  |  | X |  | 2026-04-22 | TM
CRO Advances: Any amendment modifying the repayment terms of the following advances (UC 105, 106, 107 and 108). |  |  | X |  | 2026-04-08 | FG
Headcount table |  |  | X |  | 2026-04-10 | SL AND IDA
Update of Off BS commitments if applicable (update/new commiments) |  |  | X |  | 2026-04-21 | PG/TM | "engagé" file and other
Update of the Related parties section (if new transactions) |  |  | X |  | 2026-04-27 | TM | Circulariser Dechert
Audit fees table |  |  | X |  | 2026-04-27 | TM
Backups for the FX Risk note : balances of monetary items (A/P, A/R, cash balances, etc) denominated in a foreign currency (USD only is significant) in the books of Abivax SA? |  |  | X |  | 2026-04-24 | DJ | Transmis à Q3 : • les comptes de dépôt de garantie CITI Bank & les produits à recevoir • la situation du compte bancaire USD • les CAT : o CODEIS o le compte à préavis (NCA) • la balance générale avec les comptes surlignés • le compte courant avec Abivax LLC • les comptes fournisseurs en USD (les autres devises sont NS)
Oraganization - DOA - Analytics update as of December 2025 |  |  | X |  | 2026-04-21 | FG
MD&A | [6 empty] | MD&A section title
Amount of CIR and audit track |  |  | X |  | 2026-04-22 | TM/DJ
P&L By function FR GAAP (Financials light Abivax SA & LLC) |  |  | X |  | 2026-04-22 | FG
"Devise 2026" File (foreign currency transactions backup) |  |  | X |  | 2026-04-15 | JC/PG
x

## Timeline FY25
[16 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
|  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | 2: January; 6: February; 12: March; 15: April; 19: May; 23: June; 28: July; 32: August; 36: September; 41: October; 45: November; 49: December; 2: January; 6: February; 10: March; 15: April; 19: May; 23: June
|  | Week commencing |  | 7 | 14 | 21 | 28 | 4 | 11 | 28 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 4 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 26
Q2 2025 | bar: October 7 to May 26; June 16 to August 25; September 8 to September 29
To be confirmed by Abivax |  | Abx / InExtenso - Cut-off deadline |  | July 7: 7
To be confirmed by Abivax |  | Abx / InExtenso - Internal accounts review | bar: July 7
To be confirmed by Abivax |  | Abx / Certent: IFRS 2 results |  | July 14: 15
To be confirmed by Abivax |  | Abx / InExtenso - Balance French & U.S. |  | July 14: 15
To confirm with CFGI |  | CFGI - H1 25 valuation works |  | July 7: 7
|  | KPMG - IAS19 Report |  | July 7: 11
|  | KPMG - Royalty certificates fair value |  | July 7: 9; July 14: Assuming no BP update
|  | KPMG - Financial instruments valuation works |  | July 7: 9
|  | KPMG - IFRS FS (Excel balance & tables) |  | July 14: 15
|  | KPMG - IFRS FS (Word notes to the FS) |  | July 28: 30
KPMG - French document rollforward in Workiva | bar: June 2
Abx - 6-K document rollforward in Workiva | bar: June 2
Abx "MD&A" draft and PY figures | bar: June 2; July 14 to July 21
KPMG - "MD&A" (input of HY25 figures & review) | bar: July 28
|  | KPMG - Translation from 6-K |  | August 4: 2025-08-04
|  | Abx - Preparation of the RFS |  | August 4: 04/08=>05/08
To be confirmed with Workiva |  | Workiva - 6-K Tagging |  | August 4: 30/07=>7/08; August 18: Tagging requirement to be confirmed
To be confirmed by PwC |  | PwC - Limited review HY 2025 French GAAP + Abx LLC |  | July 21: x; August 18: closing meeting on July 23th (French GAAP / LLC)
To be confirmed by PwC |  | PwC - Limited review HY 2025 IFRS | bar: July 28 to August 4
To be confirmed by PwC |  | PwC - Review of 6-K | bar: August 4
To be confirmed by PwC |  | PwC - Review of HY Financial report |  | August 4: 06/08=>08/08
|  | Audit Committee |  | August 4: 6
|  | Board Meeting |  | August 4: 6
|  | 6-K filing |  | August 11: 11
|  | HY Financial report filing |  | August 11: 11
Q3 2025 | bar: October 7 to May 26; June 16 to August 25; September 8 to September 29
To be confirmed by Abivax |  | Abx / InExtenso - Cut-off deadline |  | October 6: 8
To be confirmed by Abivax |  | Abx / InExtenso - Internal accounts review | bar: October 6
To be confirmed by Abivax |  | Abx / Certent: IFRS 2 results |  | October 13: 15
To be confirmed by Abivax |  | Abx / InExtenso - Balance French & U.S. |  | October 13: 17
To confirm with CFGI |  | CFGI - Q3 25 valuation works |  | October 6: 7
|  | KPMG - IAS19 Report |  | October 6: 13
|  | KPMG - Royalty certificates fair value |  | October 6: 9; October 13: Assuming no BP update => Confirmed, no BP update
|  | KPMG - Financial instruments valuation works |  | October 6: 9
KPMG - IFRS FS (Excel balance & tables) | bar: September 29; October 20 to October 27
KPMG - IFRS FS (Word notes to the FS) | bar: October 27 to November 3
KPMG - French document rollforward in Workiva | bar: September 1
Abx - 6-K document rollforward in Workiva | bar: September 1
Abx "MD&A" draft and PY figures | bar: September 1; October 20 to October 27
KPMG - "MD&A" (input of Q325 figures & review) | bar: November 3
KPMG - Translation from 6-K | bar: October 6; November 3 to November 10
Abx - Preparation of the RFS | bar: November 3 to November 17
To be confirmed with Workiva |  | Workiva - 6-K Tagging | bar: November 3 to November 17
To be confirmed by PwC | To be completed by PwC | PwC - Limited review HY 2025 French GAAP + Abx LLC |  | November 24: closing meeting on November 3 (French GAAP / LLC)
To be confirmed by PwC | To be completed by PwC | PwC - Limited review Q3 2025 IFRS | bar: November 10 to November 24
To be confirmed by PwC | To be completed by PwC | PwC - Review of 6-K | bar: November 3 to November 24
To be confirmed by PwC | To be completed by PwC | PwC - Review of Q3 Financial report | bar: November 17 to November 24
|  | Audit Committee |  | December 8: 11
|  | Board Meeting |  | December 8: 11
|  | 6-K filing |  | December 15: 15
|  | Q3 Financial report filing |  | December 15: 15
FY 2025 | bar: October 7 to May 26; June 16 to August 25; September 8 to September 29
To be confirmed by Abivax | To be completed by Abivax | Abx / InExtenso - Cut-off deadline |  | January 4: 8
To be confirmed by Abivax | To be completed by Abivax | Abx / InExtenso - Internal accounts review | bar: January 4
To be confirmed by Abivax | To be completed by Abivax | Abx / Certent: IFRS 2 results |  | January 12: 16
To be confirmed by Abivax | To be completed by Abivax | Abx / InExtenso - Balance French & U.S. |  | January 12: 16
To confirm with CFGI |  | CFGI - FY 25 valuation works |  | January 4: 8
|  | KPMG - IAS19 Report |  | January 4: 12
|  | KPMG - Royalty certificates fair value |  | January 4: 12; January 12: Assuming no BP update
|  | KPMG - Financial instruments valuation works |  | January 4: 12
|  | KPMG - IFRS FS (Excel balance & tables) |  | November 3: to be discussed
KPMG - IFRS FS (Word notes to the FS) | bar: January 26 to February 2
|  | KPMG - French document rollforward in Workiva |  | November 3: to be discussed
|  | Abx - 20F document rollforward in Workiva |  | November 3: to be discussed
|  | Abx "MD&A" draft and PY figures |  | November 3: to be discussed
KPMG - "MD&A" (input of FY25 figures & review) | bar: February 2
KPMG - Translation from 20F | bar: December 29; February 2 to February 9
Abx - Preparation of the URD | bar: December 29; February 2 to February 16
To be confirmed with Workiva |  | Workiva - 20-F Tagging | bar: February 2 to February 16
|  | KPMG - URD Tagging |  | January 6: mapping update; February 24: PFS; February 3: notes; January 12: mapping update; February 9: PFS; February 16: notes
To be confirmed by PwC | To be completed by PwC | PwC - Audit of FY2025 French GAAP + Abx LLC |  | February 23: closing meeting on social (French GAAP / LLC) ?
To be confirmed by PwC | To be completed by PwC | PwC - Limited review FY 2025 IFRS | bar: February 9 to February 23
To be confirmed by PwC | To be completed by PwC | PwC - Review of 20-F | bar: February 2 to February 23
To be confirmed by PwC | To be completed by PwC | PwC - Review of URD | bar: February 16 to March 2
| To be completed by PwC | PwC - Review of URD tagging | bar: February 23 to March 2
|  | Audit Committee |  | February 16: To be confirmed
Board Meeting | bar: March 16
|  | 20-F filing |  | March 23: 23
|  | URD filing |  | March 23: 23
| To be completed by Abivax | General Meeting | (not yet defined)
Note on AS11: Trinidad Mesa: In the morning if not on the 11th end of day

## Q3 2025 closing & PBC
Closing timeline / PBC List ABIVAX Local GAAP & IFRS | to complete by Abivax
2025-09-30
Item | (Q3 2025: applicable?) | Status | Target | Owner | Comments | revue du contrôle
French GAAP - Abx SA
Provision for contingencies and charges | X | Done | 2025-10-16 | PG | Circularisation à faire | ok
Provision for Forex | X | Done | 2025-10-16 | DJ |  | ok
Fixed assets: identification of invoices | X | Done | 2025-09-26 | PG |  | ok
Fixed assets : réceipt from IE FA follow up | X | Done | 2025-10-03 | In Extenso/PG |  | ok
Fixed assets: entries depreciation | X | Done | 2025-10-03 | In Extenso |  | ok
Fixed assets: table of change in PP&E & intangibles | X | Done | 2025-10-03 | In Extenso |  | ok
New fixed assets (new building : invoice and deposit) | X | Done | 2025-09-26 | PG |  | ok
Financial fixed assets | X | Done |  | PG |  | ok | J'ai rajouté cette ligne car le contrôle est fait et formalisé et indépendant des autres immobilisations
Liquidity contract | N/A | N/A | N/A
Review 471 (compte d'attente) | X | Done | 2025-09-29 | PG | A regarder régulièrement
Payroll entries | X | Done | 2025-09-29 | ADP/ PG | Comptabilisation de l'OD de paie
Rapprochement compta//Journal de paie | X | Done | 2025-09-29 | PG |  | ok
Rapprochement compa//DSN//Journal de paie | X | Done | 2025-10-06 | PG | Dépendant de la mise à disposition des DSN par ADP
Revus des dettes sociales | X | Done | 2025-10-06 | PG |  | ok
Welcome Bonus spread | X | Done | 2025-09-16 | PG |  | ok
Accrual for paid leave | X | Done | 2025-09-30 | ADP/ PG | Dépendant de la mise à disposition du document par ADP | ok
Accrual social charges on free shares | X | Done | 2025-10-10 | Trinidad/PG |  | ok
Bonus' accruals | X | Done | 2025-09-30 | Trinidad/PG |  | ok
Directors' Fees | X | Done | 2025-09-24 | Trinidad/PG |  | ok
HR traffic ( Exit and Plan) | X | Done | 2025-10-06 | Trinidad/PG
Bank reconciliation EUR | X | Done | 2025-10-03 | JC |  | ok
Bank reconciliation USD and Account Réévaluation | X | Done | 2025-10-03 | DJ |  | ok
Reconciliation of NCA accounts and CAT and reevaluation of USD account | X | Done | 2025-10-03 | DJ |  | ok
End of invoice entries | X | Done | 2025-10-06 | JC
Lettering AP | X | Done | 2025-10-03 | All
Rent Hausmann (spread) | X | Done | 2025-09-12 | PG |  | ok
Advance (CRO) | X | Done | 2025-10-09 | PG / Denis | Uniquement pour le soc il faudra attendre que les FNP soient chargées dans financial light et la MAJ par Fred des coûts par projets | ok | finalement y compris revu de la partie pour les IFRS
Prepaid preparation | X | Done | 2025-10-07 | JC
Prepaid entries | X | Done | 2025-10-09 | JC |  | ok
Circularisation interne | X | Done | 2025-09-12 | FP&A and PG
A/P: Accruals calculation (cut-off) R et D | X | Done | 2025-10-08 | FP&A |  | ok
A/P: Accruals calculation (cut-off) Marketing | X | Done | 2025-10-08 | Matt |  | ok
A/P: Accruals calculation (cut-off) ADMIN | X | Done | 2025-10-08 | PG |  | ok
A/P: Accrual entries | X | Done | 2025-10-13 | JC | Ensure that all budget owners are circulated | ok
Reevaluation of Forex for AP | X | Done | 2025-10-10 | DJ |  | ok
CIR: Obtain Time sheet | X | Done | 2025-10-07 | TM | Faire demande à E. Leveau (absente jusqu'au 6/10/2025)
CIR: calculation & entries | X | Done | 2025-10-14 | DJ/TM |  | ok
Contribution AGEPIPH et autres taxes | X | Done | 2025-09-17 | PG | certaines taxes serront calculées avec la paie | ok
Tax result calculation | X | Done | 2025-10-22 | PG | including accumulated tax losses
VAT CALCULATION | X | Done | 2025-10-15 | JC/DJ | Possibilité avant | ok
Financial instruments: obtain information on new Debt if any (legal documents, payment schedule and transaction costs) | N/A | N/A | N/A | TM/DJ
Financial instruments: entries | X | Done | 2025-09-26 | DJ |  | ok
Financial instruments: recap of Kreos/Claret & Heights French GAAP entries (bridge) | X | Done | 2025-09-26 | DJ | Revoir les informations | ok
Financial instruments: table of change in financial instruments | X | N/A | NA | In Extenso/DJ | Lié au contrat de liquidité
Interest PGE | X | Done | 2025-09-26 | DJ |  | ok
Accrued Interest on investement (NAC and CAT or DAT if any) | X | Done | 2025-10-06 | DJ | Pour les CAT, on peut anticiper | ok
Royalty certificates: Business Plan | Confirmed: no update | N/A |  | FP&A | BP provided to KPMG on the 19th of December 2024 no update as of 15/09/2025
Royalty certificates: Fair value | X | Done | 2025-10-15 | KPMG
Royalty certificates: Entry | X | Done | 2025-10-16 | PG |  | ok
Calculation of Abivax LLC recharge to Abivax SA | X | Done | 2025-10-16 | DJ / Trinidad |  | ok
Accrued Interest calculation on LLC current account | X | Done | 2025-10-16 | DJ |  | ok
IC reconciliation | X | Done | 2025-10-16 | DJ |  | ok
IC current account revaluation | X | Done | 2025-10-16 | DJ |  | ok
Autres produits (ADS Citibank) | X | Done |  | PG | Circulariser Citibank via Hema | ok | J'ai rajouté cette ligne car le contrôle est fait (pour inclure la circularisation de Hema dans le planning)
Off balancesheet commitment | X | Done | 2025-10-13 | PG/KPMG | Engagé and PIDR/IAS19 (For PIDR : HR to send payroll information to KPMG)
Table of change in equity | X | Done | 2025-10-13 | PG/Trinidad |  | ok
Trial Balance | X | Done | 2025-10-17 | PG/TM | End of day, 20th morning at the latest |  | ok sent to KPMG on the 20th ( including LLC)
General ledger | X | Done | 2025-10-17 | PG/TM | End of day, 20th morning at the latest
Close Period | X |  | 2025-10-17 | DJ | Not in the system - the closing in the system once social reviewed by auditors
Plaquette |  |  |  | DJ | No French plaquette for quarters
Extourne OD Q3 2025 | X |  | 2025-10-31 | In Extenso/PG/TM
Local GAAP - Abx LLC
Payroll entries | X | Done | 2025-10-02 | MATT
Bonus accrual | X | Done | 2025-10-02 | MATT
Social charges on Bonus accrual | X | Done | 2025-10-02 | MATT
Welcome Bonus spread | X | Done | 2025-10-02 | MATT
Bank reconciliation USD | X | Done | 2025-10-03 | MATT
Lettering AP and bank | X | Done | 2025-10-03 | MATT
A/P: Accruals calculation (cut-off) MKT & ADMIN | X | Done | 2025-10-09 | MATT
A/P: Accrual entries | X | Done | 2025-10-13 | MATT
Local GAAP TB and General Ledger Abx LLC (without IC recharge) | X | Done | 2025-10-16 | MATT
Abivax LLC recharge to Abivax SA entries | X | Done | 2025-10-16 | MATT / DJ
Fixed assets: identification of invoices | X | Done | 2025-10-06 | MATT
Fixed assets: entries | X | Done | 2025-10-07 | MATT
Fixed assets: table of change in PP&E | X | Done | 2025-10-07 | MATT
Local GAAP TB and General Ledger Abx LLC (with identification of I/C balances) | X | Done | 2025-10-17 | MATT | End of day, 20th morning at the latest
Close Period | X |  |  | DJ ? (or MATT) | At the same time as SA
Tax result calculation | ? |  | 2025-10-22
IFRS (to be confirmed by KPMG)
P&L By function FR GAAP (Financials light Abivax SA & LLC) | X |  | 2025-10-21 | FG
Additional short-term investment contracts | X |  | asap | RS
CFGI analyses of any new financing if applicable | N/A |  | N/A
Amortized cost schedule (Tr B and Tr C if applicable) | X |  | 2025-10-17 | HK
CFGI: debts exctinction memo & related accounting entries in IFRS (Heights / Kreos/Claret OCABSA & warrants) | X |  | 2025-10-07 | CFGI / HK
CFGI new debts valuations as of 30/09/25 - K/C Minimum Return Indemnifications valuations - FV of K/C debt components | X | cf tab CFGI Valuations | 2025-10-07 | CFGI / HK
EPS: Purchases/sale of Treasury shares report | N/A |  |  | TM | N/A
IFRS 2/EPS: Cap table including the BCE/BSA/AGA movements | X |  | asap | TM | ASAP Cap table ready => 10/10/2025
IFRS 2 : Updates on departures | X |  | asap | TM | Info from Ida & Sophie => 07/10/2025
IFRS 2 : new share-based payments plans if applicable | ? |  | asap | TM | Circulate Ida =>02/10/2025
IFRS 2 Results from Certent's calculation tool | X |  | 2025-10-17 | ME
IFRS 2 : Social charges accrual details with short term / long term split | X |  | 2025-10-25 | PG/TM
IAS 19 : required data for the valuation report | X |  | 2025-10-10 | SL | Request sent by KPMG to SL / IH
IFRS 16 : new leases of lease modifications if applicable | X |  | asap | TM/PG | If any new lease => None for the moment
Royalty certificates : sensitivity analyses | X |  | 2025-10-10 | KPMG
CRO advances : update on the recap file (new advances, progress% (recorded expenses / total budgeted contract expenses)) as of the closing date | X |  | 2025-10-20 | TM | Need Update on forecast with related contract made by FP&A and study cost follow-up (including forecast update)
Headcount table | X | Done | 2025-10-17 | SL AND IDA
Update of Off BS commitments if applicable (update/new commiments) | X |  | 2025-10-27 | TM | "engagé" file and other
Update of the Related parties section (if new transactions) | X |  | 2025-10-27 | TM | Circulariser Dechert
Audit fees table |  |  |  |  | Not required for Q3
"Devise 2025" File (foreign currency transactions backup) | X | Done | 2025-10-17 | JC/PG
Oraganization - DOA - Analytics update as of September 2025 | X |  | 2025-10-21 | FG | Additional request - file transmitted in Q1 2025. Containing employees' breakdown by functional area.
MD&A |  |  |  |  | MD&A section title
Amount of CIR and audit track | X |  | 2025-10-21 | TM/DJ
P&L By function FR GAAP (Financials light Abivax SA & LLC) | X |  | 2025-10-21 | FG
"Devise 2025" File (foreign currency transactions backup) | X |  | 2025-10-21 | JC/PG
x

## TimelineQ125
[14 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
|  | October |  |  |  | November |  |  |  | December |  |  |  | 2: January; 6: February; 12: March; 15: April; 19: May; 23: June; 28: July; 32: August; 36: September
| Week commencing | 7 | 14 | 21 | 28 | 4 | 11 | 28 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29
Q3 2024
| Abx / InExtenso - Balance French & U.S. | October 14: 18
| Abx / Certent: IFRS 2 results | October 21: 25
| CFGI - FY24 new debt & derivatives valuation works | October 21: 25
KPMG - Q324 IFRS FS (Excel balance & tables) | bar: November 4 to November 25
FY 2024
To be completed by Abivax | Abx / InExtenso - Cut-off deadline | January 13: 10
To be completed by Abivax | Abx / InExtenso - Internal accounts review | bar: January 13
| Abx / InExtenso - Balance French & U.S. | January 13: 17; January 27: SA/LLC balances ready
| Abx / Certent: IFRS 2 results | January 13: 17; January 27: tentative
To be completed by Abivax | CFGI - FY24 new debt & derivatives valuation works | January 6: 10
| KPMG - FY24 IAS19 Report | January 13: 17
| KPMG - Royalty certificates fair value | January 13: 15; February 10: BP available end of November / discussion to be scheduled in December
| KPMG - FY24 Financial instruments valuation works | January 13: 15
KPMG - FY24 IFRS FS (Excel balance & tables) | bar: January 20 to February 3
| KPMG - FY24 IFRS FS (Word notes to the FS) | November 28: Preparation of the FY wording & links; February 17: 19
KPMG - 20-F / URD rollforward in Workiva | bar: November 28; December 9
| Abx MD&A draft | November 28: Preparation of the FY wording & links; February 17: Abx to prepare the first draft (wording) based on the F-1 // KPMG to review and complete the initial draft and prepare the tables (IFRS figures)
| KPMG - FY24 MD&A | November 28: Preparation of the FY wording & links
| KPMG - URD Translation from 20-F | February 17: 19; February 24: FS on 28/02
To be confirmed with Workiva | Workiva - 20-F Tagging | bar: February 24 to March 17
| KPMG - URD Tagging | January 6: mapping update; February 24: PFS; February 3: notes
To be completed by PwC | PwC - French GAAP Audit + Abivax LLC | bar: January 27 to February 3
To be completed by PwC | PwC - IFRS Audit (incl. Notes) | bar: February 10 to February 24
To be completed by PwC | PwC - Review of 20-F | February 17: 19
To be completed by PwC | PwC - Review of URD | bar: February 3 to March 17
To be completed by PwC | PwC - Review of URD tagging | February 3: PFS; March 17: notes
| Audit Committee | March 17: 19; March 24: updated
| Board Meeting | March 17: 20
| 20-F publication | March 24: 24; March 31: updated
| URD publication | March 24: 24; March 31: updated
General Meeting | bar: March 31 to April 28
Q1 2025
To be confirmed by Abivax | Abx / Finalization of French GAAP Q1 24 | March 17: Timing to be confirmed by ABIVAX
To confirm with CFGI ? | CFGI - new debts / modification Memo | bar: February 17 to February 3
To be confirmed by PwC | PwC - Audit of new debt / modification | bar: February 24 to February 10
Abx / InExtenso - Cut-off deadline | bar: April 7
Abx / InExtenso - Internal accounts review | bar: April 7
| Abx / InExtenso - Balance French & U.S. | April 14: 14; April 28: SA/LLC balances ready
| Abx / Certent: IFRS 2 results | April 7: 11; April 28: tentative. Same timing as HY24. Please note that Monday 21 is a holiday
To confirm with CFGI | CFGI - Q125 valuation works | April 7: 7
| KPMG - Q125 IAS19 Report | April 7: 11
| KPMG - Royalty certificates fair value | April 7: 11; April 21: Assuming no BP update
| KPMG - Q125 Financial instruments valuation works | April 7: 11
| KPMG - Q125 IFRS FS (Excel balance & tables) | April 14: *; April 28: *; May 5: *Part-time (resource issue / bank holidays)
KPMG - Q125 IFRS FS (Word notes to the FS) | bar: March 24; April 21 to April 28
KPMG -French document rollforward in Workiva | bar: February 24
Abx - 6-K rollforward in Workiva | bar: February 24
| Abx Item 5 draft | February 10: Preparation of wording & links; May 12: Abx to prepare the first draft (wording) based on the F-1 // KPMG to review and complete the initial draft and prepare the tables (IFRS figures)
KPMG - Q125 MD&A | bar: April 28
| KPMG - Translation from 6-K | April 7: 7; May 5: *
Abx - Preparation of the RFT | bar: May 5 to May 12
To be confirmed with Workiva | Workiva - 6-K Tagging | June 9: Tagging requirement to be confirmed
To be confirmed by PwC | PwC - French GAAP Limited review + Abivax LLC | bar: April 14 to April 21
To be confirmed by PwC | PwC - IFRS Limited review (incl. Notes) | bar: May 5 to May 19
To be confirmed by PwC | PwC - Review of 6-K | bar: April 28 to May 19
To be confirmed by PwC | PwC - Review of Q1 financial report | bar: May 12 to May 19
To be confirmed by Abivax | Audit Committee | May 19: 23
To be confirmed by Abivax | Board Meeting | May 26: 26; June 2: Board on the 26th to be confirmed
To be confirmed by Abivax | 6-K filing | May 26: 28
To be confirmed by Abivax | French Q1 Financial report filing | May 26: 28
| Assumed French holiday period | April 21: 21; April 28: 1-2; May 5: 5-9; May 26: 29
21/04, 1/05, 8/05 and 29/05 are public holidays
Q1 25 SOx
| KPMG - FY25 RCM review during the week started March 24 | March 24: 25-28; March 31: ?
KPMG - D&I | bar: May 19 to July 28
PwC - Round 1&2 of Sox audit (Walkthrough) | bar: May 19 to July 28
To confirm with KPMG Sox Team | Abivax to address recommendations / control deficiencies | bar: May 19 to July 28
| PwC - Round 3 of Sox audit (ToE+additional WT if needed) | June 9: Timing of SOX works TBD
KPMG - ToE | bar: May 19 to July 28
KPMG to address recommendations / control deficiencies | bar: May 19 to July 28
Q2 2025
To be confirmed by Abivax | Abx / InExtenso - Cut-off deadline | July 7: 7
To be confirmed by Abivax | Abx / InExtenso - Internal accounts review | bar: July 7
To be confirmed by Abivax | Abx / Certent: IFRS 2 results | July 14: 15
To be confirmed by Abivax | Abx / InExtenso - Balance French & U.S. | July 14: 15
To confirm with CFGI | CFGI - H1 25 s valuation works | July 7: 7
| KPMG - IAS19 Report | July 7: 11
| KPMG - Royalty certificates fair value | July 7: 9; July 14: Assuming no BP update
| KPMG - Financial instruments valuation works | July 7: 9
| KPMG - IFRS FS (Excel balance & tables) | July 14: 15
| KPMG - IFRS FS (Word notes to the FS) | July 28: 30
KPMG - French document rollforward in Workiva | bar: June 2
Abx - 6-K document rollforward in Workiva | bar: June 2
Abx "MD&A" draft and PY figures | bar: June 2; July 14 to July 21
KPMG - "MD&A" (input of HY25 figures & review) | bar: July 28
| KPMG - Translation from 6-K | August 4: 2025-08-04
| Abx - Preparation of the RFS | August 4: 04/08=>05/08
To be confirmed with Workiva | Workiva - 6-K Tagging | August 4: 30/07=>7/08; August 18: Tagging requirement to be confirmed
To be confirmed by PwC | PwC - Limited review HY 2025 French GAAP + Abx LLC | July 21: x; August 18: closing meeting on July 23th (French GAAP / LLC)
To be confirmed by PwC | PwC - Limited review HY 2024 IFRS | bar: July 28 to August 4
To be confirmed by PwC | PwC - Review of 6-K | bar: August 4
To be confirmed by PwC | PwC - Review of HY Financial report | August 4: 06/08=>08/08
| Audit Committee | August 4: 6 - TBC
| Board Meeting | August 4: 6
| 6-K filing | August 11: 11
| HY Financial report filing | August 11: 11

## TimelineFY24
|  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February | [5 empty] | March |  |  | April
| Week commencing | 7 | 14 | 21 | 28 | 4 | 11 | 28 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 1 | 8 | 15 | 22
Q3 2024
| Abx / InExtenso - Balance French & U.S. | October 14: 18
| Abx / Certent: IFRS 2 results | October 21: 25
| CFGI - FY24 new debt & derivatives valuation works | October 21: 25
KPMG - Q324 IFRS FS (Excel balance & tables) | bar: November 4 to November 25
FY 2024
To be completed by Abivax | Abx / InExtenso - Cut-off deadline | bar: January 13
To be completed by Abivax | Abx / InExtenso - Internal accounts review | bar: January 13
| Abx / InExtenso - Balance French & U.S. | January 13: 17; January 27: SA/LLC balances ready
| Abx / Certent: IFRS 2 results | January 13: 17; January 27: tentative
To be confirmed by CFGI/Abx | CFGI - FY24 new debt & derivatives valuation works | January 6: 10
| KPMG - FY24 IAS19 Report | January 13: 17
| KPMG - Royalty certificates fair value | January 13: 15; February 10: BP available end of November / discussion to be scheduled in December
| KPMG - FY24 Financial instruments valuation works | January 13: 15
KPMG - FY24 IFRS FS (Excel balance & tables) | bar: January 20 to February 3
| KPMG - FY24 IFRS FS (Word notes to the FS) | November 28: Preparation of the FY wording & links; February 17: 19
KPMG - 20-F / URD rollforward in Workiva | bar: December 16
To be confirmed by Abivax | Abx MD&A draft | November 28: Preparation of the FY wording & links; February 17: Abx to prepare the first draft (wording) based on the F-1 // KPMG to review and complete the initial draft and prepare the tables (IFRS figures)
| KPMG - FY24 MD&A | November 28: Preparation of the FY wording & links
| KPMG - URD Translation from 20-F | February 17: 19
To be confirmed with Workiva | Workiva - 20-F Tagging | bar: February 24 to March 17
| KPMG - URD Tagging | December 16: mapping update; February 24: PFS; February 3: notes
To be completed by PwC | PwC - French GAAP Audit + Abivax LLC | bar: January 20 to February 3
To be completed by PwC | PwC - IFRS Audit (incl. Notes) | bar: February 10 to February 24
To be completed by PwC | PwC - Review of 20-F | February 17: 19
To be completed by PwC | PwC - Review of URD | bar: February 3 to March 17
To be completed by PwC | PwC - Review of URD tagging | February 3: PFS; March 17: notes
| Audit Committee | February 10: 13
| Board Meeting | March 17: 20
| 20-F publication | March 24: 25
| URD publication | March 24: 25
General Meeting | bar: March 31 to April 22

## Workiva 20-F
WORKIVA - 20-F
Item 5 | Operating and Financial Review and Prospects
| ABIVAX | KPMG
Wording | Draft | Review
Tables | Review | X (including links)
Item 11 | Quantitative and Qualitative Disclosures About Market Risk (formerly in the MD&A)
| ABIVAX | KPMG
Wording | Review | Draft (extract from the financial statements)
Tables | Review + data (see PBC list) | X (including links)
Item 15 | Controls and Procedures
| ABIVAX | KPMG
Wording | Draft | Review (Enis Team)
Tables | Draft | Review (Enis Team)
Financial statements (appendix)
| ABIVAX | KPMG | WORKIVA
Wording | Review | Draft
Tables | Review | Draft (inluding links)
Tagging |  |  | X

## TimelineFY23
| December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April
Week commencing | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29
20-F publication | April 8: tentative
URD publication | April 8: tentative
Audit Committee | March 25: 26; April 1: tentative
Board Meeting | March 25: 28
General Meeting | bar: April 15 to April 29
Workiva - 20-F Tagging | bar: February 26 to March 4
KPMG - URD Tagging | February 12: PFS; March 18: notes
Abx - 20-F structure | December 11: 14
KPMG - URD structure modifications | bar: December 25 to January 15
KPMG - URD Translation from 20-F | February 26: Financial statements
Abx / InExtenso - Cut-off deadline | January 15: 15
Abx / InExtenso - Internal accounts review | January 15: 17
Abx / InExtenso - Balance French & U.S. | January 15: 19; January 22: SA/LLC balances ready
Abx / Certent: IFRS 2 results | January 15: 19; January 22: tentative
CFGI - FY23 new debt valuation works | January 15: 15
KPMG - IFRS 2 Valuations | bar: December 4 to December 11
KPMG - FY23 IAS19 Report | January 22: 22
KPMG - Royalty certificates fair value | February 5: BP & WACC discussion meeting on Jan 8 / finalized BP available on Friday Jan 12
KPMG - FY23 Financial instruments valuation works | January 22: 22
KPMG - FY23 IFRS FS (Excel balance & tables) | bar: January 22 to February 5
KPMG - FY23 IFRS FS (Word notes to the FS) | bar: February 5 to February 19
Abx MD&A draft | February 12: Abx to prepare the first draft (wording) based on the F-1 // KPMG to review and complete the initial draft and prepare the tables (IFRS figures)
KPMG - FY23 MD&A | bar: February 12 to February 19
PwC - French GAAP Audit + Abivax LLC | bar: January 29 to February 5
PwC - IFRS Audit (incl. Notes) | bar: February 12 to March 4
PwC - Review of 20-F | bar: March 4 to March 11
PwC - Review of URD | bar: March 4 to March 25
PwC - dry-run tagging review | bar: December 11
Note on R11: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Comparison of English and French PFS tagging: TBD once Workiva timing is known
Note on H13: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : 20-F creation in Workiva
Note on J13: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : URD creation in Workiva

## TimelineHY24
| December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September
Week commencing | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30
FY23
20-F publication | April 8: tentative
URD publication | April 8: tentative
Audit Committee | March 25: 26; April 1: tentative
Board Meeting | March 25: 28
General Meeting | bar: April 15 to April 29
Workiva - 20-F Tagging | bar: February 26 to March 4
KPMG - URD Tagging | February 12: PFS; March 18: notes
Abx - 20-F structure | December 11: 14
KPMG - URD structure modifications | bar: December 25 to January 15
KPMG - URD Translation from 20-F | February 26: Financial statements
Abx / InExtenso - Cut-off deadline | January 15: 15
Abx / InExtenso - Internal accounts review | January 15: 17
Abx / InExtenso - Balance French & U.S. | January 15: 19; January 22: SA/LLC balances ready
Abx / Certent: IFRS 2 results | January 15: 19; January 22: tentative
CFGI - FY23 new debt valuation works | January 15: 15
KPMG - IFRS 2 Valuations | bar: December 4 to December 11
KPMG - FY23 IAS19 Report | January 22: 22
KPMG - Royalty certificates fair value | February 5: BP & WACC discussion meeting on Jan 8 / finalized BP available on Friday Jan 12
KPMG - FY23 Financial instruments valuation works | January 22: 22
KPMG - FY23 IFRS FS (Excel balance & tables) | bar: January 22 to February 5
KPMG - FY23 IFRS FS (Word notes to the FS) | bar: February 5 to February 19
Abx MD&A draft | February 12: Abx to prepare the first draft (wording) based on the F-1 // KPMG to review and complete the initial draft and prepare the tables (IFRS figures)
KPMG - FY23 MD&A | bar: February 12 to February 19
PwC - French GAAP Audit + Abivax LLC | bar: January 29 to February 5
PwC - IFRS Audit (incl. Notes) | bar: February 12 to March 4
PwC - Review of 20-F | bar: March 4 to March 11
PwC - Review of URD | bar: March 4 to March 25
PwC - dry-run tagging review | bar: December 11
Q124
Abx / InExtenso - Balance French & U.S. | April 22: 25
Abx / InExtenso - Balance US GAAP | April 22: 29?
CFGI - new debt valuation works | bar: May 6
KPMG - IFRS FS (Excel balance & tables) | April 29: 2; May 6: 1; May 13: 5; May 20: 2.5
KPMG - IFRS FS (Word notes to the FS) | April 29: N/A
SOx
KPMG - WP implementation | bar: April 15 to April 29
KPMG - Next steps (incl answers to PwC) | bar: April 29 to July 29
PwC - Round 1&2 of Sox audit (Walkthrough) | July 29: Meeting: Management's responses
Abivax to address recommendations / control deficiencies | July 15: 19; July 29: 2
PwC - Round 3 of Sox audit (ToE+additional WT if needed) | July 15: Meeting: PWC's report & recommendations; September 9: PWC to confirm
HY24
Workiva - 6-K Tagging | bar: July 22 to July 29
Abx - 6-K structure preparation | June 10: 14
KPMG - 6K structure review
KPMG - URD Translation from 6-K | bar: June 24 to July 1; July 29 to August 5
Abx / InExtenso - Balance French & U.S. | July 8: 11; July 22: SA/LLC balances ready
CFGI - updated memo (tranche B) | April 29: 3
PwC - validation of the memo (K/C Tr B) & valuation meeting (CVI) | bar: May 27
CFGI - new debt valuation works | July 8: 8
KPMG - IAS19 Report | July 15: 16
KPMG - Royalty certificates fair value | July 8: 11
KPMG - Financial instruments valuation works | July 15: 19
KPMG - IFRS FS (Excel balance & tables) | July 8: 12
KPMG - IFRS FS (Word notes to the FS) | bar: June 10 to June 17; July 22 to July 29
Abx "MD&A" draft and PY figures | bar: July 15 to July 22
KPMG - "MD&A" (input of HY24 figures & review) | bar: July 22
PwC - Limited review HY 2024 French GAAP + Abx LLC | July 22: closing meeting on July 24th (French GAAP / LLC)
PwC - Limited review HY 2024 IFRS | bar: July 22 to July 29
PwC - Review of 6-K | bar: August 5; August 26 to September 2
PwC - Review of HY Financial report | bar: August 5; August 26 to September 2
6-K publication | bar: September 9
HY Financial report publication | bar: September 9
Audit Committee | September 2: 4th
Board Meeting | July 1: BP sent on July 5; July 8: 11 (Board); September 2: 5th
General Meeting
PWC's proposed schedule:
Note on R12: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Comparison of English and French PFS tagging: TBD once Workiva timing is known
Note on H14: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : 20-F creation in Workiva
Note on J14: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : URD creation in Workiva