## Slide 1
ABIVAX
Board
ERP Readout
March 19, 2026
Board of Directors
Key Topics
ERP Selection Decision
Selection Process Recap
NetSuite — Rationale
Delivery Risk & Mitigations
Board Ask — Next 90 Days
CONFIDENTIAL · NOT FOR DISTRIBUTION

## Slide 2
ABIVAX · CONFIDENTIAL
Context · Slide 1 of 5
Mandate and Timing
2 / 6
Board ERP Readout · March 19, 2026
Jan 1, 2027
Go-Live Target
Non-negotiable program anchor
~10 months
Time Remaining
From April implementation start
Mar 19
Board Checkpoint
This cycle — lock direction
01
ERP/SOX is a 2026 Finance Priority
Declared priority with executive sponsorship. Selection process completed Sep 2025–Feb 2026 with full KPMG-supported methodology.
02
Jan 1, 2027 Go-Live is Non-Negotiable
Target supports US public launch (Dec 2027) and commercial scaling commitments. Delay now compounds execution and control risk exponentially.
03
March 19 Locks Direction
Board decision this cycle should confirm NetSuite selection, implementation governance owners, and the path to early April mobilization start.

## Slide 3
ABIVAX · CONFIDENTIAL
Process · Slide 2 of 5
What Has Been Completed
3 / 6
Board ERP Readout · March 19, 2026
Structured 6-phase selection process — Sep 2025 to Feb 2026 — with full documentation at each stage.
1
Initiate & Scope
Sep – Oct 2025
Program charter
ERP selection scope
Governance model
›
2
Diagnostic
Oct – Nov 2025
Pain-point mapping
Process gap analysis
Key stakeholder inputs
›
3
RFP & Requirements
Nov – Dec 2025
Requirements finalized
RFP issued to vendors
Bidder workshops held
›
4
Bid Analysis
Jan – Feb 2026
Financial comparison
Technical scoring
Demo evaluation
›
5
Decision
Feb 26, 2026
NetSuite selected
KPMG-backed rationale
Post-selection next steps
Source: KPMG-supported RFP analysis, financial comparison workbook, demo evaluations — all documented in SharePoint.

## Slide 4
ABIVAX · CONFIDENTIAL
Decision · Slide 3 of 5
Selection Decision Outcome
4 / 6
Board ERP Readout · March 19, 2026
✓ NetSuite Selected as Abivax ERP Platform
February 26, 2026
⚙ Execution Fit
Right-size for current Abivax organizational complexity
Implementation practicality vs. SAP's heavier dependency model
Faster path to go-live for Jan 1, 2027 target
◎ Usability
User experience suited to Abivax finance team profile
Lower change-management friction vs. enterprise-weight systems
Modern UI reduces training burden during mobilization
► Implementation Model
NetSuite ecosystem resources available for April start
KPMG-advised delivery model compatible with current setup
Commercial negotiation path is straightforward
What's Next:
Notify NetSuite / Oracle · Negotiate commercial terms · Confirm implementation mobilization scope · Target April 2026 start

## Slide 5
ABIVAX · CONFIDENTIAL
Risk · Slide 4 of 5
Top Delivery Risks and Mitigations
5 / 6
Board ERP Readout · March 19, 2026
Execution risk is now the program's primary variable. Each risk below has a named mitigation and owner path.
Manual Legacy Handoffs / Unclear Ownership
Mitigation:
Named owner matrix established by process and feed. Handoff accountability confirmed in blueprint phase before implementation start.
Control Evidence Gaps at Go-Live
Mitigation:
Control-by-design checkpoints embedded in blueprint phase. ERP milestones tied to control-closure evidence requirements.
Business Capacity Constraints
Mitigation:
Phase-based staffing commitments required before April mobilization. Finance and IT capacity confirmed against workstream load model.
Timeline Slippage Against Jan 1, 2027
Mitigation:
Weekly workstream governance and monthly executive review. Escalation protocol triggered on critical-path slippage.
High
Medium

## Slide 6
ABIVAX · CONFIDENTIAL
Ask · Slide 5 of 5
Board Decision and Next 90 Days
6 / 6
Board ERP Readout · March 19, 2026
01
Acknowledge NetSuite Selection
Confirm board recognition of NetSuite as the selected ERP platform and pivot governance focus from evaluation to implementation execution.
Didier / Board
02
Confirm Negotiation and Contracting Ownership
Designate Mike and Hema as lead contacts for commercial negotiation with Oracle/NetSuite and KPMG implementation advisor engagement.
Hema / Mike
03
Confirm Staffing and Decision Rights for Design Phase
Approve internal capacity commitments by function (Finance, IT, KPMG) ahead of April 2026 mobilization start.
Hema / IT / Finance
04
Establish Monthly Board-Ready Progress Reporting
Confirm reporting cadence: monthly executive update and board-ready progress report against Jan 1, 2027 milestones and pillar scorecard.
Mike / Board
Target: April 2026 Mobilization Start → Jan 1, 2027 Go-Live