## Slide 1
ABIVAX
ERP Program
Priorities
& Readiness
Living Executive Deck
Update weekly · Owner: Mike Markman
Last Updated
[Update date here]
Audiences
Didier Blondel (CFO / Sponsor)
Board of Directors
Audit Committee
Executive Team
Program Phase
Post-Selection →
Implementation Mobilization
NetSuite selected Feb 26, 2026
CONFIDENTIAL · EXECUTIVE USE ONLY

## Slide 2
ABIVAX ERP PROGRAM · EXECUTIVE UPDATE · LIVING DECK
Framing · Slide 1 of 5
ERP Program Mandate and Why It Matters Now
2 / 6
ERP Program — Living Executive Deck · Update weekly
◆ Jan 1, 2027 Go-Live Is Non-Negotiable
The ERP target date is directly tied to US public launch (Dec 2027) and commercialization commitments. Every month of delay increases implementation risk exponentially.
◆ ERP/SOX Is a 2026 Finance Priority
Declared as a priority with direct executive sponsorship. Selection process completed Sep 2025–Feb 2026. Program now moves to mobilization and execution.
◆ This Is a Business and Controls Program
ERP is foundational to scaling finance and controls toward commercialization. The program governs operating model design — not only a system replacement.
◆ Near-Term Decisions Drive Delivery Certainty
Executive governance quality and resourcing discipline determine delivery confidence more than vendor feature marketing. Delays in April mobilization shorten the safe delivery window.
Feb 26, 2026
NetSuite Selected
Mar 6
Audit Cmte Deck
Mar 19
Board Update
Apr 2026
Mobilization Start
Jan 1, 2027
Go-Live

## Slide 3
ABIVAX ERP PROGRAM · EXECUTIVE UPDATE · LIVING DECK
Program Focus · Slide 2 of 5
Three ERP Priorities — The Recurring Scorecard
3 / 6
ERP Program — Living Executive Deck · Update weekly
This is the canonical recurring slide for executive audiences. Status indicators update each cycle. Keep terminology consistent across board, audit, and exec decks.
P2P
P2P / Transaction Operations
Design Phase
Modernize approval workflows, vendor master, and payment control path.
20 CFTI controls
Done means:
System-enforced approval workflows
Vendor setup/validation path defined
Payment traceability to approval chain
Evidence retention by transaction type
Are we building a scalable transaction engine or recreating today's manual bottlenecks?
Reporting
Financial Reporting / Data Model
Design Phase
Improve multi-entity, multi-GAAP, and management reporting capability.
39 CFTI controls
Done means:
Target COA / cost-center design agreed
Reporting extract supports FP&A needs
Multi-entity, FX, multi-GAAP explicitly designed
Consultant dependency vs in-house scope decided
Will ERP materially improve reporting quality and reduce manual bridging?
Controls
SOX / Controls / Auditability
Gaps Identified
Design traceable, testable controls and evidence retention into the operating model.
84 CFTI controls
Done means:
Key controls mapped to named owners
Audit evidence retention defined
Deficiency/remediation ownership explicit
ERP design supports testable, traceable controls
Does the ERP make controls more defensible and auditable, or move the same risk into a new system?

## Slide 4
ABIVAX ERP PROGRAM · EXECUTIVE UPDATE · LIVING DECK
Current State · Slide 3 of 5
Baseline Reality — Manual Complexity and Control Risk
4 / 6
ERP Program — Living Executive Deck · Update weekly
What the current system landscape actually looks like — before ERP modernization.
Fragmented System Landscape
Sage 100 (primary GL), Trustpair (vendor validation), Agicap (cash), DocuShare (document management) — no integrated workflow across them
30 of 143 CFTI controls reference Sage 100 as the primary system; most rely on IT-dependent manual steps
No native audit trail from PO to payment across the full P2P chain
Reporting and Bridge Dependency
French GAAP → IFRS/SEC bridge is quarterly-paced and KPMG-dependent
39 reporting/data model controls in scope; most are manually maintained
No multi-entity, multi-GAAP native reporting capability in current stack
⚠ DATA GAPS — CONFIRM TO FINALIZE
• P2P Volume Baseline
Quantify: current P2P manual touchpoints, approval gaps, monthly transaction volumes by entity (SA/LLC), 1099-related process pain. Owner: Finance / Mike.
• Reporting Bridge Detail
Summarize: French GAAP → IFRS/SEC bridge process, who does what (internal vs KPMG), cycle timing, top failure points. Owner: Finance / KPMG.
• Controls Deficiency Inventory
Identify: current SOX/control gaps, where remediation tracking lives today, which deficiencies ERP is expected to address directly. Owner: Finance Controls.
Confirmed sources: CFTI control register (143 records, Feb 26 2026), KPMG RFP analysis, process flow diagrams. Open items: see TBD panel above.

## Slide 5
ABIVAX ERP PROGRAM · EXECUTIVE UPDATE · LIVING DECK
Readiness · Slide 4 of 5
Program Readiness, Open Decisions, and Resourcing
5 / 6
ERP Program — Living Executive Deck · Update weekly
✓ Completed
Structured selection process (Sep 2025–Feb 2026)
KPMG-supported RFP and bid analysis
Vendor demonstrations and technical scoring
Final decision: NetSuite selected Feb 26, 2026
CFTI control register generated (143 records)
⚠ Open Decisions
Commercial negotiation terms / owner
Mar 2026
Implementation scope confirmation
Mar 2026
Executive decision rights model
TBD
Internal capacity commitments by function
TBD
KPMG implementation advisory engagement
Apr 2026
⚠ Resourcing TBD
Finance (Internal)
Not confirmed
IT (Integration)
Not confirmed
KPMG (Advisory)
Engagement TBD
NetSuite (Vendor)
Pending contract
Executive Sponsor
Hema / Didier
90-Day Target Actions:
Notify NetSuite · Negotiate contract · Confirm implementation scope · Lock internal capacity · Establish governance cadence · April mobilization start

## Slide 6
ABIVAX ERP PROGRAM · EXECUTIVE UPDATE · LIVING DECK
Governance · Slide 5 of 5
What Executives Should Review Each Update
6 / 6
ERP Program — Living Executive Deck · Update weekly
This is the recurring operating cadence for this deck. Each executive update covers the same five elements — making it easy to track drift and progress over time.
01
Changes Since Last Update
Net-new evidence, decisions made, risks confirmed or resolved. Keeps each update grounded in what actually moved.
02
Pillar Status Summary
P2P / Reporting / Controls — confidence level, major blockers, and notable changes. One row per pillar, updated each cycle.
03
Decision Requests
Open items requiring executive action, with owner and due date. Escalated if unresolved for two or more update cycles.
04
Milestone Outlook
Next 30/60/90-day milestones with accountable owners. Red/amber/green status against plan. No milestone without owner.
05
What to Stop Watching
Items resolved, de-risked, or removed from scope. Keeps the update focused on live issues — not a growing list of history.
Update Rhythm
Weekly
Update pillar status + open decisions
Monthly
Full exec narrative refresh
Board cycle
Export board/audit derivative cuts
Milestone
Update milestone outlook on slippage