## Slide 1
ERP Program Overview
Audit Committee Briefing · March 2026
Prepared by: Mike Markman, VP Global ERP Lead
Status: NetSuite selected · Implementation targeted April 2026 · Go-live January 2027

## Slide 2
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Overview · 1 of 4
ERP Program Overview
NetSuite selected over SAP on February 26, 2026. Program mobilizes April 2026, go-live January 1, 2027.
01
Why We're Doing This
• Current finance systems (Sage 100) are fragmented and manual.
• Controls are inconsistent across P2P, reporting, and close processes.
• Not scalable for SEC filing scrutiny or US public market launch in 2027.
• ERP is a SOX-remediation and operational modernization program, not a technology swap.
02
Why NetSuite
• Implementation speed: 9 months vs 18+ for SAP.
• SaaS-native architecture, no on-premise infrastructure.
• Proven biotech install base with multi-GAAP and multi-entity capability.
• NetSuite-led delivery (Ali Brahmi, lead consultant), no third-party implementer needed.
03
Program Ownership
• ERP Lead: Mike Markman (VP, Global ERP)
• Executive Sponsor: Hema Keshava (CFO)
• Finance Process Lead: Trinidad Mesa (France)
• Implementation: NetSuite delivery team (Oracle)
• Advisory support: KPMG (scope TBC)
Audit Committee ERP Overview · March 2026
1 / 4

## Slide 3
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Timeline · 2 of 4
Implementation Timeline
April 2026 mobilization → December 27, 2026 go-live → January 17, 2027 post-support complete
Initiate & Design
Apr - May 2026
Configure & Build
May - Aug 2026
Test & Validate
Sep - Oct 2026
Migration & UAT
Nov - Dec 15, 2026
GO-LIVE
Dec 27
Key Pre-Conditions
Contract
• Sign-off targeted Mar 2026.
• Commercial review underway.
• License agreement and SOW in transit from Oracle.
Blueprint
• DoA matrix and vendor master cleanup required before April start.
• Finance and IT leads must be committed.
Staffing
• Finance and IT leads needed at 4-8 hrs/wk during configure and test phases.
Go-Live
• Jan 1, 2027 is non-negotiable.
• Tied to US public market launch Dec 2027.
Audit Committee ERP Overview · March 2026
2 / 4

## Slide 4
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Financials · 3 of 4
Financial Overview
Figures confirmed by KPMG. License agreement and SOW in transit from Oracle. Final commercial terms under negotiation.
Year 1 Investment
€650,129
€463,120 build + €187,009 run (annual)
3-Year Total
€1,023,264
Build + 3 years of license/support
5-Year Total
€1,398,163
Includes run cost inflation from Year 4
Build Cost Breakdown (€463,120 one-off)
Solution implementation
€269,240
Initialization
€50,640
Data recovery
€28,720
Project management
€20,960
Travel expenses
€18,000
Training
€13,920
Other (acceptance, start-up, misc)
€61,640
Annual Run Cost (€187,009 / year)
SaaS license (142 users @ €779.49/user/yr)
€109,908
Best-of-breed SaaS (Avalara, etc.)
€23,936
Support / TMA
€41,109
Other (environments, etc.)
€12,056
Users considered
142
Discount on list price
29%
Implementation man-days
392 days
Audit Committee ERP Overview · March 2026
3 / 4

## Slide 5
ABIVAX · AUDIT COMMITTEE · CONFIDENTIAL
Ask · 4 of 4
What We're Asking the Audit Committee
Three items. This is a program introduction. A controls deep-dive briefing will follow at a future meeting once remediation planning is underway.
01
Acknowledge Program Direction
• Confirm that the Abivax ERP program (NetSuite, April 2026 mobilization, January 1, 2027 go-live) is understood, on the committee's radar, and directionally endorsed.
02
Endorse SOX/Controls as the Primary Program Frame
• Confirm that this is a controls-remediation and operating-model program, not solely a technology replacement.
• SOX readiness, evidence quality, and audit traceability are non-negotiable design constraints.
03
Expect a Controls Deep-Dive at a Future Meeting
• This briefing is a program introduction.
• A separate controls-posture readout covering CFTI gap inventory, remediation cadence, and owner accountability will be prepared once the implementation blueprint phase begins.
Next: Controls posture briefing to be scheduled after blueprint phase begins (target: Q3 2026).
Audit Committee ERP Overview · March 2026
4 / 4