## Effort Detail
EFFORT DETAIL — Hours by Activity & Resource
Blue cells = estimated inputs (adjust to model scenarios) ¦ Black cells = formulas ¦ Green cells = cross-sheet links
GRAND TOTAL — ALL ACTIVITIES | 46 | 10 | 34 | 72 | 114 | 187 | 520 | 80 | 1063
Activity / Sub-Activity | Jean Arnold Coutareau | Shine Thomas | Angela DePoy | Ken Schatz | Brad Quillen | Walid Bouassida | Youness Tyamaz | Ashley Williams | Total Hours
A. Engagement Setup
Kick-off preparation & team onboarding | 2 | 1 | 1 | 2 | 1 | 4 | 6 |  | 17
Engagement scoping, RACI & methodology | 1 | 1 | 1 | 1 | 1 | 3 | 4 |  | 12
Subtotal — Engagement Setup | 3 | 2 | 2 | 3 | 2 | 7 | 10 | 0 | 29
B. Program Governance & Status Reporting
Status meetings (weekly: FR ¦ bi-weekly: US) | 20 |  |  | 20 | 20 | 39 | 80 |  | 179
Steering materials & governance reports | 8 |  |  |  |  | 18 | 40 |  | 66
Client-side action log & deliverable tracking | [6 empty] | 60 |  | 60
ABIVAX stakeholder coordination | 7 |  |  |  |  | 14 | 60 |  | 81
Subtotal — Program Governance & Status Reporting | 35 | 0 | 0 | 20 | 20 | 71 | 240 | 0 | 386
C. Business Process & Functional Support
Process requirements documentation | [5 empty] | 18 | 40 |  | 58
End-to-end transaction flow assessment | [5 empty] | 14 | 20 |  | 34
Functional design challenge & gap review | [5 empty] | 12 | 20 |  | 32
Subtotal — Business Process & Functional Support | 0 | 0 | 0 | 0 | 0 | 44 | 80 | 0 | 124
D. US NetSuite Team — Implementation Meeting Participation
Design / process walkthrough sessions (wks 1–16, 14 × 1.5 hrs) |  |  |  | 11 | 21 |  |  |  | 32
Integration working sessions (8 × 1.5 hrs) |  |  |  | 6 | 12 |  |  |  | 18
Build & configuration Q&A (10 × 1.0 hr) |  |  |  | 3 | 10 |  |  |  | 13
UAT support sessions (8 × 1.0 hr) |  |  |  | 4 | 8 |  |  |  | 12
Cutover planning & go-live support |  |  |  | 4 | 8 |  |  |  | 12
Subtotal — US NetSuite Team — Implementation Meeting Participation | 0 | 0 | 0 | 28 | 59 | 0 | 0 | 0 | 87
E. Stage Gate Reviews
Gate 1 — Project Initiation (wk 3) | 1 | 1 |  | 2 | 3 |  |  |  | 7
Gate 2 — Design Complete (wk 16) | 2 | 2 |  | 5 | 8 |  |  |  | 17
Gate 3 — Build Complete (wk 28) | 3 | 3 |  | 6 | 10 |  |  |  | 22
Gate 4 — UAT / Cutover Readiness (wk 36) | 1 | 1 |  | 4 | 7 |  |  |  | 13
Gate 5 — Go-Live & Transition (wk 39+) | 1 | 1 |  | 4 | 5 |  |  |  | 11
Subtotal — Stage Gate Reviews | 8 | 8 | 0 | 21 | 33 | 0 | 0 | 0 | 70
F. Controls-by-Design (SOX Integration)
SOX-to-NetSuite controls mapping |  |  | 16 |  |  | 10 | 10 | 40 | 76
Configuration controls review |  |  | 8 |  |  | 8 | 10 | 20 | 46
Controls validation — UAT scenarios |  |  | 8 |  |  | 5 | 10 | 20 | 43
Subtotal — Controls-by-Design (SOX Integration) | 0 | 0 | 32 | 0 | 0 | 23 | 30 | 80 | 165
G. Change Management & Adoption
Employee interviews | [5 empty] | 8 | 30 |  | 38
Change management strategy | [5 empty] | 10 | 30 |  | 40
Communications plan development | [5 empty] | 8 | 30 |  | 38
Ongoing adoption support & monitoring | [5 empty] | 8 | 60 |  | 68
SOX-integrated ways-of-working design | [5 empty] | 8 | 10 |  | 18
Subtotal — Change Management & Adoption | 0 | 0 | 0 | 0 | 0 | 42 | 160 | 0 | 202