## Slide 1: Board ERP Readout
Board | 2026-03-19
Owner: Mike Markman

## Slide 2: Executive Frame
Secure board alignment on ERP selection direction, implementation risk controls, and the first 90-day execution posture to protect Jan 1, 2027 go-live.
Selection process is rigorous and source-backed.
Primary risk is execution capacity and governance discipline.
A focused 90-day plan de-risks Jan 1, 2027 readiness.
Board focus

## Slide 3: Mandate and Timing
ERP/SOX is a declared 2026 finance priority with executive sponsorship.
Jan 1, 2027 go-live remains the operating target.
March 19 board cycle is the decision-communication checkpoint.
Delay now increases execution and control risk.
Context | Visual: timeline

## Slide 4: What Has Been Completed
Initiate and scope completed (Sep-Oct 2025).
Diagnostic and pain-point mapping completed (Oct-Nov 2025).
RFP workshops and requirements completed (Nov-Dec 2025).
Bid analysis, shortlist, and demos completed (Jan-Feb 2026).
Process | Visual: phase-map

## Slide 5: Selection Decision Outcome and Tradeoffs
Abivax team aligned on NetSuite as the selected path on February 26, 2026.
Decision reflects execution fit, usability, and implementation practicality for current organization size and constraints.
Open items now move to commercial negotiation, scope confirmation, and implementation mobilization timing.
Target remains early April mobilization to support Jan 1, 2027 go-live objective.
Decision | Visual: matrix

## Slide 6: Top Delivery Risks and Mitigations
Risk: manual legacy handoffs and unclear ownership. Mitigation: named owner matrix by process/feed.
Risk: business capacity constraints. Mitigation: phase-based staffing commitments.
Risk: control evidence gaps. Mitigation: control-by-design checkpoints in blueprint phase.
Risk: timeline slippage. Mitigation: weekly workstream governance and monthly executive review.
Risk | Visual: risk-heatmap
Process Visual Summary (source-backed)
France P2P (SA) Current vs Future State
Steps: Vendor setup / validation -> Invoice / coding / approval flow -> Payment validation and execution
Control overlays: 3
- P2P controls (3) | ERP 1 | OOS 1
- P2P controls (5) | ERP 3 | OOS 4
Reporting / FP&A Data Flow Current vs Future State
Steps: Source accounting / exports -> Bridge / consolidation / IFRS & SEC support -> Management / departmental reporting and forecast visibility
Control overlays: 3
- Reporting controls (11) | ERP 2 | Design 2 | OOS 6
- Reporting controls (17) | Design 8 | OOS 4

## Slide 7: Board Decision and Next 90 Days
Acknowledge NetSuite selection and pivot governance focus to implementation execution risk.
Confirm post-selection negotiation/contracting ownership and cadence (Mike/Hema with vendor and advisors).
Confirm staffing and decision rights for design phase mobilization ahead of early April start target.
Maintain monthly executive and board-ready progress reporting against Jan 1, 2027 target.
Ask | Visual: decision

## Slide 8: Board Decision and Actions
Confirm selection direction and implementation posture
Confirm staffing commitments for design/build/cutover
Confirm governance cadence through go-live
Authorize immediate closure of critical execution risks
Approval and governance asks